## 2021 budget calendar (2) (hidden)
SUBIC BAY METROPOLITAN AUTHORITY | [5 empty] | Annex E
2021 COB BUDGET CALENDAR
WITH FORWARD ESTIMATES for CY 2022-2023 | [8 empty] | 2016 Bcall | 2015 Bcall
NO. |  | ACTIVITY | TARGET DATE | ACTUAL DATE | KPM/DAYS | ACTION BY | Date of Actual Accomplishment | REMARKS | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| SBMA Management Strategic Planning and Budgeting |  | March 4-6, 2020 |  |  | PDO/SBMA Mgmt
| Attended 2020 COB Budget forum |  | January 15, 2020 | January 15, 2020 |  | DBM
| SBU's Strategic Planning |  |  |  |  | PDO
| Receipt of Consolidated Plans from Planning and Development Office |  | February 7, 2020 | February 7, 2020 |  | PDO
| Prepares draft of Budget Call 7 working days after receipt of PDO Consolidated Plans |  | February 14, 2020 | February 10, 2020 |  | FPBD
| Conducts Budget Forum with all departments as per schedule |  | February 27-March 2, 2020 | February 27-March 2, 2020 |  | FPBD
| Department are advised to download forms at FPBD page which includes the following: 1. Budget forms for 2020 2. Budget requirements for the accounts with Expense Account Managers (EAM) 3. Project Procurement Management Plans (PPMP) |  | February 27-March 2, 2020 | February 27-March 2, 2020 |  | FPBD/PPMD
| Departments' preparation and submission of REVENUE FORMS to FPBD |  | March 3, 2020 | March 3, 2020 |  | All revenue center
| Departments' preparation and submission of PPMP and all other forms to FPBD and EAMs |  | March 3 - 30, 2020 | March 3 - 30, 2020 |  | EAM/Dept/FPBD
1 | Receipts of Budget Forms, Budget Requirements and PPMP Forms from Departments/Offices and EAMs. |  | March 30, 2020 |  | 5 mins | EAM/FPBD |  |  | 2 | 1 | 1 | 1
2 | Evaluates and Consolidates the initial proposal from Departments/Offices and EAMs. |  | March 31 - April 21, 2020 |  | 14 days | EAM/FPBD |  |  | 1 |  |  |  | prepare schedule per SBUs at board room
Reviews the Budget Call letter
3 | Conducts Technical Budget Hearing with Mid-Year Review. |  | April 22-24, 2020 |  | 3 days | FPBD
4 | Consolidates the final proposal and re-budgeted items. |  | April 27 - May 7, 2020 |  | 8 days | FPBD
5 | Prepares presentation materials for CAPEX Outlay and submits to Priority Projects Capital Expenditures Committee (PPCEC) for final determination. |  | May 11 - 13, 2020 |  | 3 days | PDO/FPBD
6 | Finalizes and submits the consolidated PPMP to PPMD. |  | May 18 - 20, 2020 |  | 3 days | FPBD
7 | Prepares materials for presentation of the COB. |  | May 25-26, 2020 |  | 2 days | FPBD
8 | Presents the COB for approval to the Administrator, Board of Directors and Finance Committee. |  | June 8 -11, 2020 |  | 4 days | FPBD
9 | Prepares all DBM Forms for signature authorities. |  | June 15 - 23, 2020 |  | 7 days | FPBD
10 | Submits COB to DBM. |  | June 25, 2020 |  | 1 day | FPBD
|  | TOTAL |  |  | 45 days and 5 mins

## 2022 budget calendar (hidden)
SUBIC BAY METROPOLITAN AUTHORITY | [5 empty] | Annex E
2022 COB BUDGET CALENDAR
WITH FORWARD ESTIMATES for CY 2023-2024 | [8 empty] | 2016 Bcall | 2015 Bcall
NO. |  | ACTIVITY | TARGET DATE | ACTUAL DATE | KPM/DAYS | ACTION BY | Date of Actual Accomplishment | REMARKS | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| SBMA Management Strategic Planning and Budgeting |  | February 11-16, 2021 |  | 3 days | PDO/SBMA Mgmt |  | Feb 12-Holiday (Chinese New yr)
| Attended 2021 COB Budget forum |  | 1/26-28/2021 |  |  | DBM |  | DBM Circular Letter 2021-1 dtd 1/11/2021
| SBU's Strategic Planning |  |  |  |  | PDO
| Receipt of Consolidated Plans from Planning and Development Office |  | 2021-02-19 |  |  | PDO |  | assume 2 weeks after attending COB Budget Forum
| Prepares draft of Budget Call 7 working days after receipt of PDO Consolidated Plans |  | 2021-03-02 |  |  | FPBD
| Conducts Budget Forum with all departments as per schedule |  | March 12-16, 2021 |  |  | FPBD
| Department are advised to download forms at FPBD page which includes the following: 1. Budget forms for 2020 2. Budget requirements for the accounts with Expense Account Managers (EAM) 3. Project Procurement Management Plans (PPMP) |  | March 12-16, 2021 |  |  | FPBD/PPMD
| Departments' preparation and submission of REVENUE FORMS to FPBD |  | 2021-03-17 |  |  | All revenue center
| Departments' preparation and submission of PPMP and all other forms to FPBD and EAMs |  | March 17 - April 8, 2021 |  |  | EAM/Dept/FPBD |  | Holiday-Apr 1,2 (Holy Thursday and Good Friday)
1 | Receipts of Budget Forms, Budget Requirements and PPMP Forms from Departments/Offices and EAMs. |  | 2021-04-08 |  | 5 mins | EAM/FPBD |  |  | 2 | 1 | 1 | 1
2 | Evaluates and Consolidates the initial proposal from Departments/Offices and EAMs. |  | April 12 - April 29, 2021 |  | 14 days | EAM/FPBD |  | Holiday-Apr 9 (Bataan Day) | 1 |  |  |  | prepare schedule per SBUs at board room
Reviews the Budget Call letter
3 | Conducts Technical Budget Hearing with Mid-Year Review. |  | April 30-May 4, 2021 |  | 3 days | FPBD
4 | Consolidates the final proposal and re-budgeted items. |  | May 5 - 14, 2021 |  | 8 days | FPBD |  | Holiday-May 13 (Eidl al-Fitr)
5 | Prepares presentation materials for CAPEX Outlay and submits to Priority Projects Capital Expenditures Committee (PPCEC) for final determination. |  | May 17 - 19, 2021 |  | 3 days | PDO/FPBD
6 | Finalizes and submits the consolidated PPMP to PPMD. |  | May 24 - 26, 2021 |  | 3 days | FPBD
7 | Prepares materials for presentation of the COB. |  | May 28-31, 2021 |  | 2 days | FPBD
8 | Presents the COB for approval to the Administrator, Board of Directors and Finance Committee. |  | June 8 -11, 2021 |  | 4 days | FPBD
9 | Prepares all DBM Forms for signature authorities and Revised PPMP Forms from Departments/Offices and EAM. |  | June 14 - 22, 2021 |  | 7 days | EAM/Dept/FPBD
10 | Submits COB to DBM. |  | 2021-06-24 |  | 1 day | FPBD
|  | TOTAL |  |  | 45 days and 5 mins

## 2022 budget calendar-rev (hidden)
SUBIC BAY METROPOLITAN AUTHORITY | [5 empty] | Annex E
2022 COB BUDGET CALENDAR
WITH FORWARD ESTIMATES for CY 2023-2024 | [8 empty] | 2016 Bcall | 2015 Bcall
NO. |  | ACTIVITY | TARGET DATE | ACTUAL DATE | KPM/DAYS | ACTION BY | Date of Actual Accomplishment | REMARKS | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| SBMA Management Strategic Planning and Budgeting |  | 2021-02-02 | 2021-02-02 | 1 day | PDO/SBMA Mgmt |  | PDO memorandum dtd 1/13/2021
| Attended 2022 COB Budget forum |  | 1/26-28/2021 | Asynchronous |  | DBM |  | DBM Circular Letter 2021-1 dtd 1/11/2021
| SBU's Strategic Planning |  |  |  |  | PDO
| Receipt of Consolidated Plans from Planning and Development Office |  | 2021-02-11 | 2021-02-10 |  | PDO |  | assume 2 weeks after attending COB Budget Forum
| Prepares draft of Budget Call 7 working days after receipt of PDO Consolidated Plans |  | 2021-02-23 |  |  | FPBD |  | Feb 12,2021-Holiday
| Conducts Budget Forum with all departments as per schedule |  | March 5-9, 2021 |  |  | FPBD
| Department are advised to download forms at FPBD page which includes the following: 1. Budget forms for 2022 2. Budget requirements for the accounts with Expense Account Managers (EAM) 3. Project Procurement Management Plans (PPMP) |  | March 5-9, 2021 |  |  | FPBD/PPMD
| Departments' preparation and submission of REVENUE FORMS to FPBD |  | 2021-03-10 |  |  | All revenue center
| Departments' preparation and submission of PPMP and all other forms to FPBD and EAMs |  | March 10 - March 29, 2021 |  |  | EAM/Dept/FPBD
1 | Receipts of Budget Forms, Budget Requirements and PPMP Forms from Departments/Offices and EAMs. |  | 2021-03-29 |  | 5 mins | EAM/FPBD |  |  | 2 | 1 | 1 | 1
2 | Evaluates and Consolidates the initial proposal from Departments/Offices and EAMs. |  | Mach 30 - April 21, 2021 |  | 14 days | EAM/FPBD |  | Holiday-Apr 1,2 (Holy Thursday and Good Friday)/ Holiday-Apr 9 (Bataan Day) | 1 |  |  |  | prepare schedule per SBUs at board room
Reviews the Budget Call letter
3 | Conducts Technical Budget Hearing with Mid-Year Review. |  | April 22-April 26, 2021 |  | 3 days | FPBD
4 | Consolidates the final proposal and re-budgeted items. |  | April 27- May 6, 2021 |  | 8 days | FPBD
5 | Prepares presentation materials for CAPEX Outlay and submits to Priority Projects Capital Expenditures Committee (PPCEC) for final determination. |  | May 7 - 11, 2021 |  | 3 days | PDO/FPBD
6 | Finalizes and submits the consolidated PPMP to PPMD. |  | May 12 - 17, 2021 |  | 3 days | FPBD |  | Holiday-May 13 (Eidl al-Fitr)
7 | Prepares materials for presentation of the COB. |  | May 19-20, 2021 |  | 2 days | FPBD
8 | Presents the COB for approval to the Administrator, Board of Directors and Finance Committee. |  | May 21 -26, 2021 |  | 4 days | FPBD
9 | Prepares all DBM Forms for signature authorities and Revised PPMP Forms from Departments/Offices and EAM. |  | May 27 - June 4, 2021 |  | 7 days | EAM/Dept/FPBD
10 | Submits COB to DBM. |  | 2021-06-08 |  | 1 day | FPBD
|  | TOTAL |  |  | 45 days and 5 mins
Formulas:
ACTUAL DATE = [TARGET DATE]

## 2022 budget calendar-rev FINAL (hidden)
SUBIC BAY METROPOLITAN AUTHORITY | [5 empty] | Annex E
2022 COB BUDGET CALENDAR
WITH FORWARD ESTIMATES for CY 2023-2024 | [9 empty] | 2016 Bcall | 2015 Bcall
NO. |  | ACTIVITY | TARGET DATE | ACTUAL DATE | KPM/DAYS | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| SBMA Management Strategic Planning and Budgeting |  | 2021-02-02 | 2021-02-02 | 1 day | PDO/SBMA Mgmt |  | PDO memorandum dtd 1/13/2021
| Attended 2022 COB Budget forum |  | 1/26-28/2021 | Asynchronous |  | DBM |  | DBM Circular Letter 2021-1 dtd 1/11/2021
| SBU's Strategic Planning |  |  |  |  | PDO
| Receipt of Consolidated Plans from Planning and Development Office |  | 2021-02-11 | 2021-02-10 |  | PDO |  | assume 2 weeks after attending COB Budget Forum
| Prepares draft of Budget Call 7 working days after receipt of PDO Consolidated Plans |  | 2021-02-23 |  |  | FPBD |  | Feb 12,2021-Holiday
| Conducts Budget Forum with all departments as per schedule |  | March 5-9, 2021 |  |  | FPBD
| Department are advised to download forms at FPBD page which includes the following: 1. Budget forms for 2022 2. Budget requirements for the accounts with Expense Account Managers (EAM) 3. Project Procurement Management Plans (PPMP) |  | March 5-9, 2021 |  |  | FPBD/PPMD
| Departments' preparation and submission of REVENUE FORMS to FPBD |  | 2021-03-10 |  |  | All revenue center
| Departments' preparation and submission of PPMP and all other forms to FPBD and EAMs |  | March 10 - March 29, 2021 |  |  | EAM/Dept/FPBD
1 | Receipts of Budget Forms, Budget Requirements and PPMP Forms from Departments/Offices and EAMs. |  | 2021-03-29 |  | 5 mins | EAM/FPBD |  |  |  | 2 | 1 | 1 | 1
2 | Evaluates and Consolidates the initial proposal from Departments/Offices and EAMs. |  | Mach 30 - April 21, 2021 |  | 14 days | EAM/FPBD |  | Holiday-Apr 1,2 (Holy Thursday and Good Friday)/ Holiday-Apr 9 (Bataan Day) |  | 1 |  |  |  | prepare schedule per SBUs at board room
Reviews the Budget Call letter
3 | Conducts Technical Budget Hearing with Mid-Year Review. |  | April 22-April 26, 2021 |  | 5 days | FPBD |  |  | 45
4 | Consolidates the final proposal and re-budgeted items. |  | April 22- April 28, 2021 |  |  | FPBD |  |  | 45
5 | Prepares presentation materials for CAPEX Outlay and submits to Priority Projects Capital Expenditures Committee (PPCEC) for final determination. |  | April 29, 2021 |  | 1 day | PDO/FPBD
6 | Finalizes and submits the consolidated PPMP to PPMD. |  | April 30 - May 5, 2021 |  | 4 days | FPBD |  | Holiday-May 1 (Labor Day)
7 | Prepares materials for presentation of the COB. |  | May 6-14, 2021 |  | 6 days | FPBD |  | Holiday-May 13 (Eidl al-Fitr)
8 | Presents the COB for approval to the Administrator, Board of Directors and Finance Committee. |  | May 17 -26, 2021 |  | 8 days | FPBD
9 | Prepares all DBM Forms for signature authorities and Revised PPMP Forms from Departments/Offices and EAM. |  | May 27 - June 3, 2021 |  | 6 days | EAM/Dept/FPBD
10 | Submits COB to DBM. |  | 2021-06-08 |  | 1 day | FPBD
|  | TOTAL |  |  | 45 days and 5 mins
Formulas:
ACTUAL DATE = [TARGET DATE]

## 2024 budget calendar -for PPMD (hidden)
SUBIC BAY METROPOLITAN AUTHORITY | [6 empty] | Annex E
2024 COB BUDGET CALENDAR
WITH FORWARD ESTIMATES for CY 2025-2026 | [10 empty] | 2016 Bcall | 2015 Bcall
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| SBMA Management Strategic Planning and Budgeting | [5 empty] | PDO/SBMA Mgmt |  | PDO memorandum- To be determined
| Attended 2024 COB Budget forum |  | 1/27/2023 |  | 2023-01-27 |  | DBM |  | DBM Circular Letter No. 2023-1 dtd 1/17/2023
| SBMA Management Strategic Planning and Budgeting |  | TBA |  |  |  | PDO/SBMA Mgmt |  | PDO memorandum- To be determined
| SBU's Strategic Planning | [5 empty] | PDO
| Receipt of Consolidated Plans from Planning and Development Office |  | 2023-02-16 |  |  |  | PDO |  | assume 2 weeks after attending COB Budget Forum
| Prepares draft of Budget Call 7 working days after receipt of PDO Consolidated Plans |  | 2023-02-28 |  |  |  | FPBD |  | Feb 24, 2023 -Special Holiday (Fri)/ Feb 25,2023-Holiday (Sat)
| Conducts Budget Forum with all departments as per schedule |  | March 14-17, 2023 |  |  |  | FPBD
| Department are advised to download forms at FPBD page which includes the following: 1. Budget forms for 2024 2. Budget requirements for the accounts with Expense Account Managers (EAM) 3. Project Procurement Management Plans (PPMP) |  | March 14-17, 2023 |  |  |  | FPBD/PPMD
| Departments' preparation and submission of REVENUE FORMS to FPBD |  | 2023-03-20 |  |  |  | All revenue center
| Departments' preparation and submission of PPMP and all other forms to FPBD and EAMs |  | March 20 - April 11, 2023 |  |  |  | EAM/Dept/FPBD
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
1 | Receipts of Budget Forms, Budget Requirements and PPMP Forms from Departments/Offices and EAMs. |  | 2023-04-11 | 5 mins |  |  | EAM/FPBD |  |  |  | 2 | 1 | 1 | 1
2 | Evaluates and Consolidates the initial proposal from Departments/Offices and EAMs. |  | April 11 - May 02, 2023 | 14 days |  |  | EAM/FPBD |  | Holiday-Apr 6,7 (Holy Thursday and Good Friday), April 10 (Day of Valor), April 21 (Eid al-Fitr) |  | 1 |  |  |  | prepare schedule per SBUs at board room
| Conducts Technical Budget Hearing with Mid-Year Review. |  | April 28- May 03, 2023 | 3 days |  |  | FPBD |  | Holiday-May 01 (Labor Day) | 45
3 | Consolidates the final proposal and re-budgeted items. |  | May 3- May 17, 2023 | 11 days |  |  | FPBD |  | Holiday-May 01 (Labor Day) | 45
4 | Prepares presentation materials for CAPEX Outlay and submits to Priority Projects Capital Expenditures Committee (PPCEC) for final determination. |  | May 18-June 15, 2023 | 3 days |  |  | PDO/FPBD |  | Holiday-June 12 (Independence Day)
5 | Finalizes and submits the consolidated PPMP to PPMD. |  | June 16-20,2023 | 3 days |  |  | FPBD
6 | Prepares materials for presentation of the COB. |  | June 21- July 11, 2023 | 14 days |  |  | FPBD |  | Holiday-June 28 (Eid al-Adha)
7 | Presents the COB for approval to the Finance Committee, Chairman and Administrator and Board of Directors |  | July 12-17,2023 | 4 days |  |  | FPBD
8 | Prepares all DBM Forms for signature authorities and Revised PPMP Forms from Departments/Offices and EAM. |  | July 18-27, 2023 | 7 days |  |  | EAM/Dept/FPBD
9 | Submits COB for signature/ initial of Department Manager, Deputy Administrator, Senior Deputy Administrator and Chairman |  | July 28- August 7,2023 | 7 days |  |  | FPBD
10 | Photocopies and binds the COB and attachments |  | Aug 8-10,2023 | 3 days |  |  | FPBD
11 | Submits COB to DBM. |  | August 11,2023 | 1 day |  |  | FPBD
|  | TOTAL |  | 67 days and 5 mins
Note: Achievement of the target may be affected by the factors beyond the control of FPBD.

## 2025 budget calendar (hidden)
SUBIC BAY METROPOLITAN AUTHORITY | [6 empty] | Annex E
2025 COB BUDGET CALENDAR
WITH FORWARD ESTIMATES for CY 2026-2027 | [10 empty] | 2016 Bcall | 2015 Bcall
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| SBMA Management Strategic Planning and Budgeting | [5 empty] | PDO/SBMA Mgmt |  | PDO memorandum- To be determined
| Attended 2025 COB Budget forum |  | 1/23/2024 |  | 2024-01-23 |  | DBM |  | DBM Circular Letter No. 2023-16 dtd 12/21/2023
| SBMA Management Strategic Planning |  | Feb 21-23, 2024 |  |  |  | PDO/SBMA Mgmt |  | PDO memorandum
| SBU's Strategic Planning | [5 empty] | PDO
| Receipt of Consolidated Plans from Planning and Development Office |  | 2024-03-08 |  |  |  | PDO |  | assume 2 weeks after Management Strategic Planning
| Prepares draft of Budget Call 7 working days after receipt of PDO Consolidated Plans |  | 2024-03-19 | 11 days |  |  | FPBD
| Conducts Budget Forum with all departments as per schedule |  | March 26-April 02, 2024 | 4 days |  |  | FPBD |  | Holiday-March 28-29 (Holy Thursday and Good Friday),
| Department are advised to download forms at FPBD page which includes the following: 1. Budget forms for 2025 2. Budget requirements for the accounts with Expense Account Managers (EAM) 3. Project Procurement Management Plans (PPMP) |  | March 26-April 02, 2024 |  |  |  | FPBD/PPMD
| Departments' preparation and submission of REVENUE FORMS to FPBD |  | 2024-04-11 | 5days |  |  | All revenue center |  | April 9 (Day of Valor), April 10 (Eid al-Fitr)
| Departments' preparation and submission of PPMP and all other forms to FPBD and EAMs |  | April 11 to 30, 2024 | 14 days |  |  | EAM/Dept/FPBD
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
1 | Receipts of Budget Forms, Budget Requirements and PPMP Forms from Departments/Offices and EAMs. |  | 2024-04-30 | 5 mins |  |  | EAM/FPBD |  |  |  | 2 | 1 | 1 | 1
2 | FPBD and EAMs evaluates and consolidates the initial proposal from Departments/Offices and EAMs. |  | May 2 - 21, 2024 | 14 days |  |  | EAM/FPBD |  | Holiday-May 01 (Labor Day) |  | 1 |  |  |  | prepare schedule per SBUs at board room
| Conducts Technical Budget Hearing with Mid-Year Review. |  | April 28- May 03, 2023 | 3 days |  |  | FPBD |  | Holiday-May 01 (Labor Day) | 45
3 | Consolidates the final proposal and re-budgeted items. |  | May 22 - June 5, 2024 | 11 days |  |  | FPBD |  |  | 45
4 | Prepares presentation materials for CAPEX Outlay and submits to Priority Projects Capital Expenditures Committee (PPCEC) for final determination. |  | June 6-10,2024 | 3 days |  |  | PDO/FPBD
5 | Finalizes and submits the consolidated PPMP to PPMD. |  | June 11 - 14, 2024 | 3 days |  |  | FPBD |  | Holiday-June 12 (Independence Day)
6 | Prepares materials for presentation of the COB. |  | June 17-25, 2024 | 7 days |  |  | FPBD
7 | Presents the COB for approval to the Finance Committee, Chairman and Administrator and Board of Directors |  | June 26 to July 01, 2024 | 4 days |  |  | FPBD
8 | Prepares all DBM Forms for signature authorities and Revised PPMP Forms from Departments/Offices and EAM. |  | July 02 -10, 2024 | 7 days |  |  | EAM/Dept/FPBD
9 | Submits COB for signature/ initial of Department Manager, Deputy Administrator, Senior Deputy Administrator and Chairman |  | July 11 - 19, 2024 | 7 days |  |  | FPBD
10 | Photocopies and binds the COB and attachments |  | July 22 - 24, 2024 | 3 days |  |  | FPBD
11 | Submits COB to DBM. |  | 2024-07-25 | 1 day |  |  | FPBD
|  | TOTAL |  | 60 days and 5 mins
Note: Achievement of the target may be affected by the factors beyond the control of FPBD.

## 2025 budget calendar -rev (hidden)
SUBIC BAY METROPOLITAN AUTHORITY | [6 empty] | Annex E
2025 COB BUDGET CALENDAR
WITH FORWARD ESTIMATES for CY 2026-2027 | [10 empty] | 2016 Bcall | 2015 Bcall
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| SBMA Management Strategic Planning and Budgeting | [5 empty] | PDO/SBMA Mgmt |  | PDO memorandum- To be determined
| Attended 2025 COB Budget forum |  | 1/23/2024 |  | 2024-01-23 |  | DBM |  | DBM Circular Letter No. 2023-16 dtd 12/21/2023
| SBMA Management Strategic Planning |  | March 4-6, 2024 |  |  |  | PDO/SBMA Mgmt |  | PDO memorandum
| SBU's Strategic Planning | [5 empty] | PDO
| Receipt of Consolidated Plans from Planning and Development Office |  | 2024-03-22 |  |  |  | PDO |  | assume 2 weeks after Management Strategic Planning
| Prepares draft of Budget Call 7 working days after receipt of PDO Consolidated Plans |  | 2024-04-05 | 11 days |  |  | FPBD |  | Holiday-March 28-29 (Holy Thursday and Good Friday),
| Conducts Budget Forum with all departments as per schedule |  | April 8-15,2024 | 4 days |  |  | FPBD |  | April 9 (Day of Valor), April 10 (Eid al-Fitr)
| Department are advised to download forms at FPBD page which includes the following: 1. Budget forms for 2025 2. Budget requirements for the accounts with Expense Account Managers (EAM) 3. Project Procurement Management Plans (PPMP) |  | April 8-15,2024 |  |  |  | FPBD/PPMD
| Departments' preparation and submission of REVENUE FORMS to FPBD |  | 2024-04-22 | 5days |  |  | All revenue center
| Departments' preparation and submission of PPMP and all other forms to FPBD and EAMs |  | April 23 to May 13, 2024 | 14 days |  |  | EAM/Dept/FPBD |  | Holiday-May 01 (Labor Day)
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
1 | Receipts of Budget Forms, Budget Requirements and PPMP Forms from Departments/Offices and EAMs. |  | 2024-05-13 | 5 mins |  |  | EAM/FPBD |  |  |  | 2 | 1 | 1 | 1
2 | FPBD and EAMs evaluates and consolidates the initial proposal from Departments/Offices and EAMs. |  | May 14 - 31, 2024 | 14 days |  |  | EAM/FPBD |  |  |  | 1 |  |  |  | prepare schedule per SBUs at board room
| Conducts Technical Budget Hearing with Mid-Year Review. |  | April 28- May 03, 2023 | 3 days |  |  | FPBD |  | Holiday-May 01 (Labor Day) | 45
3 | Consolidates the final proposal and re-budgeted items. |  | June 3-18,2024 | 11 days |  |  | FPBD |  | Holiday-June 12 (Independence Day) | 45
4 | Prepares presentation materials for CAPEX Outlay and submits to Priority Projects Capital Expenditures Committee (PPCEC) for final determination. |  | June 19-21,2024 | 3 days |  |  | PDO/FPBD
5 | Finalizes and submits the consolidated PPMP to PPMD. |  | June 24 - 26, 2024 | 3 days |  |  | FPBD
6 | Prepares materials for presentation of the COB. |  | June 27 to July 05, 2024 | 7 days |  |  | FPBD
7 | Presents the COB for approval to the Finance Committee, Chairman and Administrator and Board of Directors |  | July 08-11, 2024 | 4 days |  |  | FPBD
8 | Prepares all DBM Forms for signature authorities and Revised PPMP Forms from Departments/Offices and EAM. |  | July 12 -22, 2024 | 7 days |  |  | EAM/Dept/FPBD
9 | Submits COB for signature/ initial of Department Manager, Deputy Administrator, Senior Deputy Administrator and Chairman |  | July 23 - 31, 2024 | 7 days |  |  | FPBD
10 | Photocopies and binds the COB and attachments |  | Aug 1 - 5, 2024 | 3 days |  |  | FPBD
11 | Submits COB to DBM. |  | 2024-08-06 | 1 day |  |  | FPBD
|  | TOTAL |  | 60 days and 5 mins
Note: Achievement of the target may be affected by the factors beyond the control of FPBD.

## 2025 budget calendar -final (hidden)
SUBIC BAY METROPOLITAN AUTHORITY | [6 empty] | Annex E
2025 COB BUDGET CALENDAR
WITH FORWARD ESTIMATES for CY 2026-2027 | [10 empty] | 2016 Bcall | 2015 Bcall
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| SBMA Management Strategic Planning and Budgeting | [5 empty] | PDO/SBMA Mgmt |  | PDO memorandum- To be determined
| Attended 2025 COB Budget forum |  | 1/23/2024 |  | 2024-01-23 |  | DBM |  | DBM Circular Letter No. 2023-16 dtd 12/21/2023
| SBMA Management Strategic Planning |  | April 17 -19, 2024 |  |  |  | PDO/SBMA Mgmt |  | PDO memorandum
| SBU's Strategic Planning | [5 empty] | PDO
| Receipt of Consolidated Plans from Planning and Development Office |  | 2024-05-03 |  |  |  | PDO |  | assume 2 weeks after Management Strategic Planning/ Holiday-May 01 (Labor Day)
| Prepares draft of Budget Call 7 working days after receipt of PDO Consolidated Plans |  | 2024-05-14 | 11 days |  |  | FPBD
| Conducts Budget Forum with all departments as per schedule |  | May 29 - June 03,2024 | 4 days |  |  | FPBD
| Department are advised to download forms at FPBD page which includes the following: 1. Budget forms for 2025 2. Budget requirements for the accounts with Expense Account Managers (EAM) 3. Project Procurement Management Plans (PPMP) |  | May 29 - June 03,2024 |  |  |  | FPBD/PPMD
| Departments' preparation and submission of REVENUE FORMS to FPBD |  | 2024-06-10 | 5days |  |  | All revenue center
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| Departments' preparation and submission of PPMP and all other forms to FPBD and EAMs |  | June 11 to July 01, 2024 | 14 days |  |  | EAM/Dept/FPBD |  | Holiday-June 12 (Independence Day)
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
1 | Receipts of Budget Forms, Budget Requirements and PPMP Forms from Departments/Offices and EAMs. |  | 2024-07-01 | 5 mins |  |  | EAM/FPBD |  |  |  | 2 | 1 | 1 | 1
2 | FPBD and EAMs evaluates and consolidates the initial proposal from Departments/Offices and EAMs. |  | July 02 - July 19, 2024 | 14 days |  |  | EAM/FPBD |  |  |  | 1 |  |  |  | prepare schedule per SBUs at board room
| Conducts Technical Budget Hearing with Mid-Year Review. |  | April 28- May 03, 2023 | 3 days |  |  | FPBD |  | Holiday-May 01 (Labor Day) | 45
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
3 | Consolidates the final proposal and re-budgeted items. |  | July 22-Aug 05,2024 | 11 days |  |  | FPBD |  |  | 45
4 | Prepares presentation materials for CAPEX Outlay and submits to Priority Projects Capital Expenditures Committee (PPCEC) for final determination. |  | Aug 06-08,2024 | 3 days |  |  | PDO/FPBD
5 | Finalizes and submits the consolidated PPMP to PPMD. |  | Aug 09 - 13, 2024 | 3 days |  |  | FPBD
6 | Prepares materials for presentation of the COB. |  | Aug 14 - 27, 2024 | 7 days |  |  | FPBD |  | Holiday-Aug 21 (Ninoy Aquino Day)/ Aug 26 (National Heroes Day)
7 | Presents the COB for approval to the Finance Committee, Chairman and Administrator and Board of Directors |  | Aug 28 to Sept 02, 2024 | 4 days |  |  | FPBD
8 | Prepares all DBM Forms for signature authorities and Revised PPMP Forms from Departments/Offices and EAM. |  | Sept 03 -11, 2024 | 7 days |  |  | EAM/Dept/FPBD
9 | Submits COB for signature/ initial of Department Manager, Deputy Administrator, Senior Deputy Administrator and Chairman |  | Sept 12 - 20, 2024 | 7 days |  |  | FPBD
10 | Photocopies and binds the COB and attachments |  | Sept 23 - 25, 2024 | 3 days |  |  | FPBD
11 | Submits COB to DBM. |  | 2024-09-26 | 1 day |  |  | FPBD
|  | TOTAL | 60 days and 5 mins | 60 days and 5 mins
Note: Achievement of the target may be affected by the factors beyond the control of FPBD.

## 2026 budget calendar (hidden)
SUBIC BAY METROPOLITAN AUTHORITY | [6 empty] | Annex E
2026 COB BUDGET CALENDAR
WITH FORWARD ESTIMATES for CY 2027-2028 | [10 empty] | 2016 Bcall | 2015 Bcall
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| SBMA Management Strategic Planning and Budgeting | [5 empty] | PDO/SBMA Mgmt |  | PDO memorandum- To be determined
| Attended 2026 COB Budget forum |  | 1/28/2025 |  | 2025-01-28 |  | DBM |  | National Budget Memorandum No. 153 dtd 12/27/2024
| SBMA Management Strategic Planning |  | January 14-17, 2025 |  |  |  | PDO/SBMA Mgmt |  | PDO memorandum dtd 11/12/2024
| SBU's Strategic Planning | [5 empty] | PDO
| Receipt of Consolidated Plans from Planning and Development Office |  | 2025-02-03 |  |  |  | PDO |  | assume 2 weeks after Management Strategic Planning/ Holiday-January 17 (James Leonard T. Gordon Day)/ January 29 (Chinese New Year)
| Prepares draft of Budget Call 7 working days after receipt of PDO Consolidated Plans |  | 2025-02-12 | 11 days |  |  | FPBD
| Conducts Budget Forum with all departments as per schedule |  | March 03 - March 06,2025 | 4 days |  |  | FPBD
| Department are advised to download forms at FPBD page which includes the following: 1. Budget forms for 2026 2. Budget requirements for the accounts with Expense Account Managers (EAM) 3. Project Procurement Management Plans (PPMP) |  | March 03 - March 06,2025 |  |  |  | FPBD/PPMD
| Departments' preparation and submission of REVENUE FORMS to FPBD |  | 2025-03-14 | 5days |  |  | All revenue center
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| Departments' preparation and submission of PPMP and all other forms to FPBD and EAMs |  | March 17 to Apr 01, 2025 | 14 days |  |  | EAM/Dept/FPBD |  | Holiday-March 31 (Eidul-Fitar)
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
1 | Receipts of Budget Forms, Budget Requirements and PPMP Forms from Departments/Offices and EAMs. |  | 2025-04-01 | 5 mins |  |  | EAM/FPBD |  |  |  | 2 | 1 | 1 | 1
2 | FPBD and EAMs evaluates and consolidates the initial proposal from Departments/Offices and EAMs. |  | April 02 - April 29, 2025 | 14 days |  |  | EAM/FPBD |  | Holiday-April 9 (The Day of Valor)/Apr 17 (Maundy Thursday)/ Apr 18 (Good Friday) |  | 1 |  |  |  | prepare schedule per SBUs at board room
| Conducts Technical Budget Hearing with Mid-Year Review. |  | April 28- May 03, 2023 | 3 days |  |  | FPBD |  | Holiday-May 01 (Labor Day) | 45
NO. |  | ACTIVITY | TARGET DATE | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
3 | Consolidates the final proposal and re-budgeted items. |  | April 30-May 15,2025 | 11 days |  |  | FPBD |  | Holiday- May 1 (Labor Day) | 45
4 | Prepares presentation materials for CAPEX Outlay and submits to Priority Projects Capital Expenditures Committee (PPCEC) for final determination. |  | May 16-20,2025 | 3 days |  |  | PDO/FPBD
5 | Finalizes and submits the consolidated PPMP to PPMD. |  | May 21 - 23, 2025 | 3 days |  |  | FPBD
6 | Prepares materials for presentation of the COB. |  | May 26 - June 6, 2025 | 7 days |  |  | FPBD
7 | Presents the COB for approval to the Finance Committee, Chairman and Administrator and Board of Directors |  | June 9 to June 13, 2025 | 4 days |  |  | FPBD |  | Holiday - June 12 (Independence Day)
8 | Prepares all DBM Forms for signature authorities and Revised PPMP Forms from Departments/Offices and EAM. |  | June 16 -24, 2025 | 7 days |  |  | EAM/Dept/FPBD
9 | Submits COB for signature/ initial of Department Manager, Deputy Administrator, Senior Deputy Administrator and Chairman |  | June 25 - July 03, 2025 | 7 days |  |  | FPBD
10 | Photocopies and binds the COB and attachments |  | July 04 - 08, 2025 | 3 days |  |  | FPBD
11 | Submits COB to DBM. |  | 2025-07-09 | 1 day |  |  | FPBD
|  | TOTAL | 60 days and 5 mins | 60 days and 5 mins
Note: Achievement of the target may be affected by the factors beyond the control of FPBD.

## 2027 Budget Calendar
SUBIC BAY METROPOLITAN AUTHORITY | [7 empty] | Annex E
2027 COB BUDGET CALENDAR
WITH FORWARD ESTIMATES for CY 2028-2029 | [11 empty] | 2016 Bcall | 2015 Bcall
NO. |  | ACTIVITY | TARGET DATE | POC | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| SBMA Management Strategic Planning and Budgeting | [6 empty] | PDO/SBMA Mgmt |  | PDO memorandum- To be determined
| Attended 2027 COB Budget forum |  | 1/29/2026 |  |  | 2026-01-29 |  | DBM |  | National Budget Memorandum No. 156 dated 01/05/2026
| SBMA Management Strategic Planning |  | February 18-20, 2026 |  |  | February 18-20, 2026 |  | PDO/SBMA Mgmt |  | Office Order No. 2026-01-274/ Authority to Travel dated 2/16/2026
| SBU's Strategic Planning | [6 empty] | PDO
| Receipt of Consolidated Plans from Planning and Development Office (PDO) |  | 2026-03-13 |  | 8 days | 2026-03-12 |  | PDO |  | Estimated at 2 weeks after Management Strategic Planning. Received thru email dtd March 12, 2026
| Prepares draft of Budget Call 7 working days after receipt of PDO Consolidated Plans |  | 2026-03-24 |  |  |  |  | FPBD
| Conducts Budget Forum with all departments as per schedule |  | Apr 7 - Apr 14, 2026 |  |  |  |  | FPBD |  | Holiday - Apr 2, 2026 (Maundy Thursday), 04/03/2026 (Good Friday), 04/19/2026 (Day of Valor)
| Department are advised to download forms at FPBD page which includes the following: 1. Budget forms for 2027 2. Budget requirements for the accounts with Expense Account Managers (EAM) 3. Project Procurement Management Plans (PPMP) |  | Apr 7 - Apr 14, 2026 |  |  |  |  | FPBD/PPMD
| Departments' preparation and submission of REVENUE FORMS to FPBD |  | Jan. 30,2026 (online)/ Feb. 06, 2026 (Hardcopy) |  | 5days |  |  | All revenue center |  | Memorandum from the Office of the Chairman and Administrator dated 01/08/2026
NO. |  | ACTIVITY | TARGET DATE |  | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| Departments' preparation and submission of Budget Forms to FPBD, PPMP to PPMD and budget request of special accounts to EAMs |  | April 13 to 30, 2026 |  | 14 days |  |  | EAM/Dept/FPBD
NO. |  | ACTIVITY | TARGET DATE |  | KPM/DAYS | ACTUAL DATE | KPM/DAYS | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
1 | Receipts of Budget Forms, Budget Requirements from Departments/Offices and EAMs. (Note: PPMP forms to be submitted to PPMD) |  | 2026-04-30 |  | 5 mins |  |  | EAM/FPBD |  |  |  | 2 | 1 | 1 | 1
2 | FPBD, PPMD and EAMs evaluates and consolidates the initial proposal from Departments/Offices and EAMs. |  | May 04 - May 26, 2026 | Budget Officers | 17 days |  |  | EAM/FPBD/PPMD |  | Holiday - May 1 (Labor Day) |  | 1 |  |  |  | prepare schedule per SBUs at board room
| Conducts Technical Budget Hearing with Mid-Year Review. |  | April 28- May 03, 2023 |  | 3 days |  |  | FPBD |  | Holiday-May 01 (Labor Day) | 45
NO. |  | ACTIVITY | TARGET DATE |  | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
3 | Consolidates the final proposal and re-budgeted items. |  | May 27-June 10,2026 | DC JAM | 11 days |  |  | FPBD |  |  | 60
NO. |  | ACTIVITY | TARGET DATE |  | KPM/DAYS | ACTUAL DATE | KPM/DAYS ACTUAL | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
4 | Prepares presentation materials for CAPEX Outlay and submits to Priority Projects Capital Expenditures Committee (PPCEC) for final determination. |  | June 11-22,2026 | DC JAM | 7 days |  |  | PDO/FPBD |  | Holiday - June 12 (Independence Day) | 63
5 | Presentation of CAPEX outlays to the selected members of the Board for approval together with FPBD, PPMD and EAMs |  | June 23-July 06, 2026 | FPBD | 10 days |  |  | EAM/FPBD/PPMD
6 | Finalizes and submits the consolidated PPMP to PPMD. |  | July 07-July 09, 2026 | DC JAM | 3 days |  |  | FPBD
7 | Prepares materials for presentation of the COB. |  | July 10-20,2026 | DC JAM | 7 days |  |  | FPBD | [8 empty] | 63
8 | Presents the COB for approval to the Chairman and Administrator, Finance Committee and Board of Directors |  | July 21 to July 24, 2026 | FPBD | 4 days |  |  | FPBD
8 | Prepares all DBM Forms for signature authorities and Revised PPMP Forms from Departments/Offices and EAM. |  | July 11 to July 21, 2025 |  | 7 days |  |  | EAM/Dept/FPBD
9 | Submits COB for signature/ initial of Department Manager, Deputy Administrator, Senior Deputy Administrator and Chairman |  | July 22 to July 30, 2025 |  | 7 days |  |  | FPBD
10 | Photocopies and binds the COB and attachments |  | July 31 -Aug 04, 2025 |  | 3 days |  |  | FPBD
11 | Submits COB to DBM. |  | 2025-08-05 |  | 1 day |  |  | FPBD
9 | Prepares and submits the proposed 2027 COB to all Delivery Units(Dus) and Departments/Offices |  | July 27-30, 2026 | Budget Officers | 4 days |  |  | FPBD
|  | TOTAL | 63 days and 5 mins |  | 63 days and 5 mins
Note: Achievement of the target may be affected by the factors beyond the control of FPBD.

## 2020 budget calendar (hidden)
SUBIC BAY METROPOLITAN AUTHORITY | [5 empty] | Annex E
2020 COB BUDGET CALENDAR | [7 empty] | 65
WITH FORWARD ESTIMATES for CY 2021-2022 | [9 empty] | 2016 Bcall | 2015 Bcall
NO. |  | ACTIVITY | TARGET DATE | ACTUAL DATE | KPM/DAYS | ACTION BY | Date of Actual Accomplishment | REMARKS |  | NO OF DAYS | NO OF DAYS | Difference |  | ACTUAL DATE
| Sbma Management Strategic Planning and Budgeting |  | December 10, 2018 |  | n/a | PDO/ SBMA Mgmt. | February 7-9, 2018 |  | ok
| Attended 2020 COB Budget forum |  | January 25,2019 |  | n/a | DBM | 2018-01-19 |  | ok
| SBU's Strategic Planning |  | March 05 - Apr 4, 2019 | April 11, 2019 | n/a | PDO
| Receipt of Consolidated Plans from Planning and Development Office |  | April 9, 2019 | April 16, 2019 | n/a | PDO
1 | Prepares draft of Budget Call 7 working days after receipt of PDO Consolidated Plans |  | April 15,2019 | April 12, 2019 |  | FPBD | 2018-04-19 |  |  | 2 | 1 | 1 | 1
2 | Reviews the Budget Call Memorandum |  | April 15-21, 2019 | April 12-21, 2019 | 5 | FPBD/DA-FINANCE/SDA- SUPPORT | Apr. 23, 2018 Apr. 26, 2018 |  |  | 1 |  |  |  | prepare schedule per SBUs at board room
| Reviews the Budget Call letter |  | Apr. 27 - 30, 2018 |  |  | ADMINISTRATOR | 2018-04-28
3 | Distribute the Budget Call to all departments |  | April 22,2019 | April 22, 2019 | 1 | FPBD | 2018-05-04
4 | Conducts Budget Forum with all departments as per schedule |  | April 24-26, 2019 | April 24-26, 2019 | 3 | FPBD/ PPMD | May 9-11 , 2018
5 | Department are advised to download forms at FPBD page which includes the following: 1. Budget forms for 2020 2. Budget requirements for the accounts with Expense Account Managers (EAM) 3. Project Procurement Management Plans (PPMP) |  | April 24-26, 2019 | April 24-26, 2019 |  | FPBD/ PPMD | May 9-11 , 2018
6 | Departments' preparation and submission of REVENUE FORMS to FPBD |  | April 24 - May 14,2019 | April 24 - May 14,2019 | 1 | ALL REVENUE CTR DEPARTMENTS | Same as target
7 | Departments' preparation and submission of PPMP and all other forms to FPBD and EAMs |  | April 29-May 20, 2019 | April 29, 2019 | 21 | EAM/FPBD
8 | Review by EAM and Submission to FPBD for review, evaluation & consolidation |  | May 21 to June 10, 2019 |  | 28 | EAM/FPBD
9 | Conducts Technical Budget Hearing for the proposed 2020 COB with updated BUR report and 2019 review. |  | June 19- 21, 2019 | June 19- 21, 2019 | 3 | FPBD
10 | Submission of Rebudgeted items |  | June 19- 21, 2019 |  | 3 | FPBD
11 | Validates, consolidates and finalizes 2020 Budget proposal and rebudgeted items |  | June 24-28, 2019 |  | 5 | FPBD/CAPEX Comm.
12 | Submits to PPCEC (Priority Project Capital Expenditure Committee) |  | July 2, 2019 |  | 1 | FPBD/CAPEX Comm.
13 | PPCEC (Priority Project Capital Expenditure Committee) Evaluation |  | July 3-4, 2019 |  | 2 | CAPEX Comm.
14 | FPBD revises 2020 budget proposal as per PPCEC recommendation |  | July 5-8, 2019 |  | 2 | FPBD
15 | Prepares and submits PPMP to PPMD |  | July 9, 2019 | July 19, 2019 with Letter Request for extension | 1 | FPBD |  | Request for Extension
16 | Finalizes 2020 COB and prepares presentation materials |  | July 10 to August 25, 2019 |  | 8 | FPBD
17 | Submits and secures approval of the proposed 2020 COB by the Administrator, Finance Committee and SBMA BOD. |  |  |  | 26 | FPBD
18 | Accomplishes, signs & binds 2020 Budget forms |  |  |  | 5 | FPBD
19 | Submits 2020 COB to DBM for approval |  |  | October 8, 2019 | 1 | FPBD
|  | TOTAL |  |  | 116

## 2020 budgetforum (hidden)
Subic Bay Metropolitan Authority
Financial Planning and Budget Department
BUDGET FORUM SCHEDULE
APRIL 24,25,26, 2019
Tentative Venue: HRMD Training Room , Bldg. 662 (APRIL 24,2019)
LABOR Conference Room , Bldg. 662 (APRIL 25 - 26,2019)
SBU / DEPARTMENT / OFFICE |  | BUDGET OFFICER | SCHEDULE
LEGAL AFFAIRS GROUP |  |  | 2019-04-24
| Office of the DA for Legal Affairs | Ester Tamayo | 8:30 - 12:00
| Legal Dept. | Ester Tamayo | 8:30 - 12:00
| Labor Dept. | Ester Tamayo | 8:30 - 12:00
REGULATORY GROUP |  |  | 2019-04-24
| Office of the SDA for Regulatory Group | Lina Sarmiento | 8:30 - 12:00
| Safety Dept. | Lina Sarmiento | 8:30 - 12:00
| Ecology Center | Lina Sarmiento | 8:30 - 12:00
CHAIRMAN & ADMINISTRATOR'S GROUP |  |  | 2019-04-24
| Board Secretariat | Amy Fernandez | 8:30 - 12:00
| Chairman & Administrator's Office | Amy Fernandez | 8:30 - 12:00
| Intelligence Office | Amy Fernandez | 8:30 - 12:00
| Internal Audit Services | Amy Fernandez | 8:30 - 12:00
| Planning and Development Office | Amy Fernandez | 8:30 - 12:00
| Public Relations Office | Amy Fernandez | 8:30 - 12:00
| Media Production Office | Amy Fernandez | 8:30 - 12:00
TOURISM |  |  | 2019-04-24
| Tourism Dept. | Pat Monasterio | 8:30 - 12:00
MUNICIPAL GROUP |  |  | 2019-04-25
| Fire Dept. | Boy Peñas | 8:30 - 12:00
| Law Enforcement Dept. | Boy Peñas | 8:30 - 12:00
| Public Health Department | Boy Peñas | 8:30 - 12:00
| Office of the DA for Public Health & Safety | Boy Peñas | 8:30 - 12:00
PUBLIC WORKS & TECHNICAL SVCS GROUP |  |  | 2019-04-25
| Office of the DA for Public Works & Technical Services | Pat Monasterio | 8:30 - 12:00
| Engineering Services | Pat Monasterio | 8:30 - 12:00
| Construction and Maintenance Dept. | Pat Monasterio | 8:30 - 12:00
| Utilities | Pat Monasterio | 8:30 - 12:00
| Telecommunication Dept. | Lina Sarmiento | 8:30 - 12:00
PORT OPERATIONS GROUP |  |  | 2019-04-25
| Office of the SDA for Port Operations | Nora Sevillejo | 8:30 - 12:00
| Office of the DA for Port Operations | Nora Sevillejo | 8:30 - 12:00
| Airport Dept. | Nora Sevillejo | 8:30 - 12:00
| Seaport Dept. | Nora Sevillejo | 8:30 - 12:00
| Trade Facilitation & Compliance | Nora Sevillejo | 8:30 - 12:00
ADMINISTRATION GROUP |  |  | 2019-04-26
| Office of the SDA for Support Services | Ester Tamayo | 8:30 - 12:00
| Office of the DA for Administration | Ester Tamayo | 8:30 - 12:00
| Human Resource & Management Dept. | Ester Tamayo | 8:30 - 12:00
| Office Services Dept. | Ester Tamayo | 8:30 - 12:00
| Procurement & Property Management Dept. | Ester Tamayo | 8:30 - 12:00
| Information Technology Dept. | Nora Sevillejo | 8:30 - 12:00
FINANCE GROUP |  |  | 2019-04-26
| Office of the DA for Finance | Nora Sevillejo | 8:30 - 12:00
| Accounting Dept. | Nora Sevillejo | 8:30 - 12:00
| Financial Planning and Budget Dept | Nora Sevillejo | 8:30 - 12:00
| Treasury Dept. | Nora Sevillejo | 8:30 - 12:00
BUSINESS AND INVESTMENT GROUP |  |  | 2019-04-26
| Office of the SDA for Business & Investment | Ciel Fabros | 8:30 - 12:00
| Office of the DA Business and Investment | Ciel Fabros | 8:30 - 12:00
| Land and Asset Management Dept. | Ciel Fabros | 8:30 - 12:00
| General Business and Investment (GBID) | Ciel Fabros | 8:30 - 12:00
| Business & Investment - Leisure | Ciel Fabros | 8:30 - 12:00
| Business & Investment - Manufacturing & Maritime | Ciel Fabros | 8:30 - 12:00
| Business & Investment - ICT | Ciel Fabros | 8:30 - 12:00
| Business & Investment - Logistics | Ciel Fabros | 8:30 - 12:00
Notes:
1. Attendees should be maximum of 3 pax only:
a. Department's Manager
b. Budget Officer
c. Supply Officer
| 2. Morning session is for budget forum. |  | 8:30 - 12:00 NN
| 3. Afternoon is alloted for PPMD's presentation. |  | 1:30 - 5:00 PM

## 2020 budget hearing (hidden)
Subic Bay Metropolitan Authority
Financial Planning and Budget Department
BUDGET HEARING SCHEDULE
June 19,20,21, 2019
Tentative Venue: HRMD Training Room , Bldg. 662 (JUNE 19, 2019)
LABOR Conference Room , Bldg. 662 (JUNE 20-21,2019)
SBU / DEPARTMENT / OFFICE |  | BUDGET OFFICER | SCHEDULE
ADMINISTRATION GROUP |  |  | 2019-06-19
| Office of the SDA for Support Services | Ester Tamayo | 8:30 - 12:00
| Office of the DA for Administration | Ester Tamayo | 8:30 - 12:00
| Human Resource & Management Dept. | Ester Tamayo | 8:30 - 12:00
| Office Services Dept. | Ester Tamayo | 8:30 - 12:00
| Procurement & Property Management Dept. | Ester Tamayo | 8:30 - 12:00
| Information Technology Dept. | Nora Sevillejo | 8:30 - 12:00
LEGAL AFFAIRS GROUP |  |  | 2019-06-19
| Office of the DA for Legal Affairs | Ester Tamayo | 8:30 - 12:00
| Legal Dept. | Ester Tamayo | 8:30 - 12:00
| Labor Dept. | Ester Tamayo | 8:30 - 12:00
CHAIRMAN & ADMINISTRATOR'S GROUP |  |  | 2019-06-19
| Chairman & Administrator's Office | Amy Fernandez | 1:30 - 4:30
| Board Secretariat | Amy Fernandez | 1:30 - 4:30
| Intelligence Office | Amy Fernandez | 1:30 - 4:30
| Internal Audit Services | Amy Fernandez | 1:30 - 4:30
| Planning and Development Office | Amy Fernandez | 1:30 - 4:30
| Public Relations Office | Amy Fernandez | 1:30 - 4:30
| Media Production Office | Amy Fernandez | 1:30 - 4:30
TOURISM GROUP |  |  | 2019-06-19
| Tourism Dept. | Pat Monasterio | 1:30 - 4:30
FINANCE GROUP |  |  | 2019-06-20
| Office of the DA for Finance | Nora Sevillejo | 8:30 - 12:00
| Accounting Dept. | Nora Sevillejo | 8:30 - 12:00
| Financial Planning and Budget Dept | Nora Sevillejo | 8:30 - 12:00
| Treasury Dept. | Nora Sevillejo | 8:30 - 12:00
BUSINESS AND INVESTMENT GROUP |  |  | 2019-06-20
| Office of the SDA for Business & Investment | Ciel Fabros | 1:30 - 4:30
| Office of the DA Business and Investment | Ciel Fabros | 1:30 - 4:30
| Land and Asset Management Dept. | Ciel Fabros | 1:30 - 4:30
| General Business and Investment (GBID) | Ciel Fabros | 1:30 - 4:30
| Business & Investment - Leisure | Ciel Fabros | 1:30 - 4:30
| Business & Investment - Manufacturing & Maritime | Ciel Fabros | 1:30 - 4:30
| Business & Investment - ICT | Ciel Fabros | 1:30 - 4:30
| Business & Investment - Logistics | Ciel Fabros | 1:30 - 4:30
REGULATORY GROUP |  |  | 2019-06-21
| Office of the SDA for Regulatory Group | Lina Sarmiento | 8:30 - 12:00
| Safety Dept. | Lina Sarmiento | 8:30 - 12:00
| Ecology Center | Lina Sarmiento | 8:30 - 12:00
PUBLIC WORKS & TECHNICAL SVCS GROUP |  |  | 2019-06-21
| Office of the DA for Public Works & Technical Services | Pat Monasterio | 8:30 - 12:00
| Engineering Services | Pat Monasterio | 8:30 - 12:00
| Construction and Maintenance Dept. | Pat Monasterio | 8:30 - 12:00
| Utilities | Pat Monasterio | 8:30 - 12:00
| Telecommunication Dept. | Lina Sarmiento | 8:30 - 12:00
MUNICIPAL GROUP |  |  | 2019-06-21
| Fire Dept. | Boy Peñas | 1:30 - 4:30
| Law Enforcement Dept. | Boy Peñas | 1:30 - 4:30
| Public Health Department | Boy Peñas | 1:30 - 4:30
| Office of the DA for Public Health & Safety | Boy Peñas | 1:30 - 4:30
PORT OPERATIONS GROUP |  |  | 2019-06-21
| Office of the SDA for Port Operations | Nora Sevillejo | 1:30 - 4:30
| Office of the DA for Port Operations | Nora Sevillejo | 1:30 - 4:30
| Airport Dept. | Nora Sevillejo | 1:30 - 4:30
| Seaport Dept. | Nora Sevillejo | 1:30 - 4:30
| Trade Facilitation & Compliance | Nora Sevillejo | 1:30 - 4:30
Notes:
1. Attendees should be maximum of 3 pax only:
a. Department's Manager
b. Budget Officer
c. Supply Officer

## 2015 BUDGET FORUM (hidden)
CY 2016 BUDGET FORUM/WORKSHOP
20 May 2015, Wednesday
HRMD Conference Rm, Bldg. 662
STRATEGIC BUSINESS UNIT / DEPARTMENT / OFFICE |  | SCHEDULE
INTERNAL SERVICES GROUP |  | 9:00 - 10:30 A.M.
1 | Office of the SDA for Internal Services |  |  | 2
2 | Office of the DA for Administration |  |  | 2 |  | 13*2 | 26
3 | Human Resource & Management Dept. |  |  | 2
4 | Information Technology Dept. |  |  | 2
5 | Office Services Dept. |  |  | 2
6 | Procurement & Property Management Dept. |  |  | 2
7 | Office of the DA for Finance |  |  | 2
8 | Accounting Dept. |  |  | 2
9 | Financial Planning and Budget Dept |  |  | 2
10 | Treasury Dept. |  |  | 2
11 | Office of the DA for Legal Affairs |  |  | 2
12 | Legal Dept. |  |  | 2
13 | Labor Dept. |  |  | 2
CHAIRMAN & ADMINISTRATOR AND REGULATORY GROUP |  | 10:30 - 12:00 NOON
Board of Directors
1 | Chairman & Administrator's Office |  |  | 2 |  | 12*2 | 24
2 | Board Secretariat Office |  |  | 2
3 | Intelligence Office |  |  | 2
4 | Internal Audit Services Office |  |  | 2
5 | Planning and Development Office |  |  | 2
6 | Office of the DA for Corporate Communications |  |  | 2
7 | Public Relations Office |  |  | 2
8 | Media Production Office |  |  | 2
9 | Office of the SDA for Regulatory Group |  |  | 2
10 | Safety Dept. |  |  | 2
11 | Ecology Center |  |  | 2
12 | Transportation & Communication Dept. |  |  | 2
AVIATION AND MARITIME GROUP |  | 1:00 - 3:00 P.M.
1 | Office of the SDA for Aviation & Maritime Operations |  |  | 2 |  | 4*2 | 8
2 | Airport Dept. |  |  | 2
3 | Seaport Dept. |  |  | 2
4 | Trade Facilitation & Compliance Dept. |  |  | 2
PUBLIC SERVICES GROUP |  | 1:00 - 3:00 P.M. |  |  |  | 8*2 | 16
1 | Fire Dept. |  |  | 2
2 | Law Enforcement Dept. |  |  | 2
3 | Public Health Department |  |  | 2
4 | Office of the DA for Public Works & Technical Services |  |  | 2
5 | Engineering Services |  |  | 2
6 | Construction and Maintenance Dept.-Maintenance Div |  |  | 2
7 | Construction and Maintenance Dept.-Transportation Div |  |  | 2
8 | Office of the DA for Public Health and Safety |  |  | 2
BUSINESS AND INVESTMENT GROUP |  | 3:30 - 5:00 P.M.
1 | Office of the SDA for Business & Investment |  |  | 2 |  | 9*2 | 18
2 | Land and Asset Management Dept. |  |  | 2
3 | General Business and Investment |  |  | 2
4 | Business & Investment - Leisure |  |  | 2
5 | Business & Investment - Manufacturing & Maritime |  |  | 2
6 | Business & Investment - ICT |  |  | 2
7 | Office of the DA for Tourism/Office of the DA for Buss. Group |  |  | 2
8 | Tourism Dept. |  |  | 2
9 | Business & Investment - Logistics |  |  | 2
|  |  |  | 92 | TOTAL |  | 92
Note: |  |  | ppmd | 2 |  |  | 2
| 2 pax per dept. |  | pbb | 2
| invite PPMD for APP/PPMP |  | fcad | 14 |  |  | 15
|  |  |  | 110 |  |  | 109
46

## 2014 BUDGET FORUM (hidden)
CY 2015 BUDGET FORUM/WORKSHOP
16 June 2014, Monday
Board Room, Bldg. 229
STRATEGIC BUSINESS UNIT / DEPARTMENT / OFFICE |  | SCHEDULE
INTERNAL SERVICES GROUP |  | 9:00 - 10:30 A.M.
| Office of the SDA for Internal Services |  |  | 2
| Office of the DA for Administration |  |  | 2
| Human Resource & Management Dept. |  |  | 2
| Information Technology Dept. |  |  | 2
| Office Services Dept. |  |  | 2
| Procurement & Property Management Dept. |  |  | 2
| Office of the DA for Finance |  |  | 2
| Accounting Dept. |  |  | 2
| Financial Control & Analysis Dept |  |  | 2
| Treasury Dept. |  |  | 2
| Office of the DA for Legal Affairs |  |  | 2
| Legal Dept. |  |  | 2
| Labor Dept. |  |  | 2
CHAIRMAN & ADMINISTRATOR AND REGULATORY GROUP |  | 10:30 - 12:00 NOON
Board of Directors
| Chairman & Administrator's Office |  |  | 2
| Board Secretariat Office |  |  | 2
| Intelligence Office |  |  | 2
| Internal Audit Services Office |  |  | 2
| Planning and Development Office |  |  | 2
| Office of the DA for Corporate Communications |  |  | 2
| Public Relations Office |  |  | 2
| Media Production Office |  |  | 2
| Office of the SDA for Regulatory Group |  |  | 2
| Safety Dept. |  |  | 2
| Ecology Center |  |  | 2
| Transportation & Communication Dept. |  |  | 2
AVIATION AND MARITIME GROUP |  | 1:00 - 3:00 P.M.
| Office of the SDA for Aviation & Maritime Operations |  |  | 2
| Airport Dept. |  |  | 2
| Seaport Dept. |  |  | 2
| Trade Facilitation & Compliance |  |  | 2
PUBLIC SERVICES GROUP |  | 1:00 - 3:00 P.M.
| Fire Dept. |  |  | 2
| Law Enforcement Dept. |  |  | 2
| Public Health Department |  |  | 2
| Office of the DA for Public Works & Technical Services |  |  | 2
| Engineering Services |  |  | 2
| Construction and Maintenance Dept. |  |  | 2
BUSINESS AND INVESTMENT GROUP |  | 3:30 - 5:00 P.M.
| Office of the SDA for Business & Investment |  |  | 2
| Land and Asset Management Dept. |  |  | 2
| General Business and Investment |  |  | 2
| Business & Investment - Leisure |  |  | 2
| Business & Investment - Manufacturing & Maritime |  |  | 2
| Business & Investment - ICT |  |  | 2
| Office of the DA for Tourism |  |  | 2
| Tourism Dept. |  |  | 2
| Business & Investment - Logistics |  |  | 2
|  |  |  | 88 | TOTAL
Note: |  |  | ppmd | 2
| 2 pax per dept. |  | pbb | 2
| invite PPMD for APP/PPMP |  | fcad | 14
106

## 2014 BUDGET CALENDAR (hidden)
SUBIC BAY METROPOLITAN AUTHORITY
2015 BUDGET CALENDAR (FINAL)
WITH FORWARD ESTIMATES 2015 AND CAPEX PLAN 2015 - 2017
NO. | ACTIVITY |  | TARGET DATE | ACTION BY | NOTES / REMINDERS | NO. OF DAYS
1. | Issuance of the Budget Call for 2015 COB and 2016 - 2017 Budget Estimates including Target Amounts for specific Expense Account |  | 2014-06-16 | FCAD |  | 1
2. | Budget Forum on 2015 COB and 2016 - 2017 Budget Estimates |  | 2014-06-16 | FCAD | 2 pax per Dept./ see attached schedule
3. | a. | Budget for Specific Expense Account handled by Expense Account Managers (EAMs)
| a.1 | Preparation and Submission of Projects/Budget Requirements to designated Expense Account Managers (EAM) | June 17 - 30, 2014 | ALL DEPTS / OFFICES | 10 DAYS | 10
| a.2 | Evaluation, consolidation and scheduling of the submitted Projects / Budget Requirements by Year (2015 - 2017). Preparation of the Project Procurement Management Plans (PPMPs) for the proposed 2015 Projects / Budget Management. | July 01 - 16, 2014 | ALL EAMs | 12 DAYS | 12
| a.3 | Submission of the PPMPs covering the consolidated Projects / Budget Requirements by the EAM to FCAD. | July 16 - 17, 2014 | ALL EAMs | 2 DAYS | 2
| b. | Budget for All Other Accounts (ex. Travel, Training, etc.)
| b.1 | Preparation of the PPMPs covering Budget Estimates of All Other Expense Accounts, | June 17 - July 4, 2014 | ALL DEPTS / OFFICES |  | 14
| b.2 | Submission of the PPMPs covering the consolidated Projects / Budget Requirements by the EAM to FCAD. | July 7 - 8, 2014 | ALL DEPTS / OFFICES |  | 2
| c. | Review / Evaluation of PPMPs | July 9 - 25, 2014 | FCAD |  | 13
4. | a. | 2014 Midyear Review and Re-budgetting of Projects to 2015
| a.1 | Preparation and Distribution of Budget Utilization Report as of June 30, 2014 as basis for the 2014 Midyear Budget Review. | July 1 - 11, 2014 | FCAD | 10 days | 10
| a.2 | 2014 Midyear Budget Review - to identify Projects and Items for re-budgetting and inclusion to 2015 COB based on June Budget Utilization Report. | July 14 - 25, 2014 | ALL DEPTS / OFFICES | 2 weeks | 10
| b. | STRATPLAN MID-YEAR REVIEW
| b.1 | Preparation and Release of June 2014 Financials for the Mid-year Review to FCAD | July 01 - 15, 2014 | ACCTG. | 11 days | 11
| b.2 | Preparation of June 2014 Financial Reports for the Mid-yer Review | July 16 - 18, 2014 | FCAD | 3 days | 3
| b.3 | SBMA Stratplan - 2014 Mid-year Review and 2015 - 2017 Budget Targets | July 21 - 25, 2014 | ALL DEPTS / OFFICES | Tentative any day this week | 5
| c. | Submission of Projects / Items for Re-budgetting in 2015 | July 28 - 29, 2014 | ALL DEPTS / OFFICES | 2 days | 2
5. | Consolidation of 2014 Rebudgetted Items and 2015 Target Amounts and the Preparation of the 2014 Annualized Projection and the 2015 - 2017 Proposed Budget / per Dept. / Office |  | July 31 - Aug 15, 2014 | FCAD | 12 days | 12
6. | Technical Budget Hearings by SBU / Department / Office |  | Aug 18 - 20, 2014 | FCAD, ALL DEPTS / OFFICES | 3 days / see attached schedule | 3
7. | Validation & Finalization of 2015 Budget Proposal |  | Aug 22 - 29, 2014 | FCAD | 5 days | 5
8. | Finalization of the Proposed 2015 COB (with 2014 Rebudgetted Items) and Budget Estimates for 2016 - 2019 in Powerpoint Materials. |  | Sept 01 - 15, 2014 | FCAD |  | 15
9. | Submission of the Proposed 2015 COB to the Chairman |  | Sept 16 - 17, 2014 | FCAD |  | 2
10. | Presentation on the Proposed 2015 COB to the Chairman |  | Sept 17 - 22, 2014 | FCAD / CHAIRMAN | Tentative any day this period | 4
11. | Presentation for approval of the Proposed 2015 COB by the Board's Finance Committee during the 2nd meeting of September 2014 |  | Sept 25 - 26, 2014 | FCAD / BOD Finance Com. | Tentative any day this period | 2
12. | Presentation for the Board's Approval of the Proposed 2015 COB during the 1st BOD Meeting of October 2014 |  | Oct 09 - 10, 2014 | FCAD / BOD | Tentative | 2
13. | Preparation / Printing of 2015 Budget Documents (DBM Forms) |  | Oct 13 - 30, 2014 | FCAD |  | 14
14. | Review / Signing of 2015 Budget Documents (DBM Forms) |  | Nov. 03 - 07, 2014 | FCAD / ODA-Fin. / Chairman | 5 days | 5
15. | Photocopy / Binding and Submission of COB 2015 to the Department of Budget and Management (DBM) |  | Nov. 10 - 12, 2014 | FCAD | 3 days | 3
16. | Submission of the 2015 COB to DBM |  | Nov. 13 - 14, 2014 | FCAD | 2 days | 2
164
|  | MONTH | NO OF WORKDAYS | HOLIDAYS
|  | JUNE 16-30 | 11
|  | JULY 1-31 | 23
|  | AUG 1-31 | 19 | 2
|  | SEPT 1-30 | 22
|  | OCT 1-31 | 21 | 2
|  | NOV 1-14 | 10
106

## BUDGET HEARING 2014 (hidden)
BUDGET HEARING SCHEDULE
Venue: Board Room, Bldg. 229
SBU / DEPARTMENT / OFFICE |  | BUDGET OFFICER | SCHEDULE
BUSINESS AND INVESTMENT GROUP |  |  | 2014-08-18
| Office of the SDA for Business & Investment | Pat Monasterio | 8:30 - 11:30 A.M.
| Land and Asset Management Dept. | Pat Monasterio | 8:30 - 11:30 A.M.
| General Business and Investment | Ciel Fabros | 8:30 - 11:30 A.M.
| Business & Investment - Leisure | Ciel Fabros | 8:30 - 11:30 A.M.
| Business & Investment - Manufacturing & Maritime | Ciel Fabros | 8:30 - 11:30 A.M.
| Business & Investment - ICT | Ciel Fabros | 8:30 - 11:30 A.M.
| Business & Investment - Logistics | Ciel Fabros | 8:30 - 11:30 A.M.
| Office of the DA for Tourism | Pat Monasterio | 8:30 - 11:30 A.M.
| Tourism Dept. | Pat Monasterio | 8:30 - 11:30 A.M.
PUBLIC SERVICES GROUP |  |  | 2014-08-18
| Fire Dept. | Boy Peñas | 1:30 - 4:30 P.M.
| Law Enforcement Dept. | Boy Peñas | 1:30 - 4:30 P.M.
| Public Health Department | Boy Peñas | 1:30 - 4:30 P.M.
| Office of the DA for Public Works & Technical Services | Boy Peñas | 1:30 - 4:30 P.M.
| Engineering Services | Boy Peñas | 1:30 - 4:30 P.M.
| Construction and Maintenance Dept. | Pat Monasterio | 1:30 - 4:30 P.M.
REGULATORY GROUP |  |  | 2014-08-19
| Office of the SDA for Regulatory Group | Lina Sarmiento | 8:30 - 11:30 A.M.
| Safety Dept. | Lina Sarmiento | 8:30 - 11:30 A.M.
| Ecology Center | Lina Sarmiento | 8:30 - 11:30 A.M.
| Transportation & Communication Dept. | Lina Sarmiento | 8:30 - 11:30 A.M.
AVIATION AND MARITIME GROUP |  |  | 2014-08-19
| Office of the SDA for Aviation & Maritime Operations | Nora Sevillejo | 1:30 - 4:30 P.M.
| Airport Dept. | Nora Sevillejo | 1:30 - 4:30 P.M.
| Seaport Dept. | Nora Sevillejo | 1:30 - 4:30 P.M.
| Trade Facilitation & Compliance | Nora Sevillejo | 1:30 - 4:30 P.M.
CHAIRMAN & ADMINISTRATOR'S GROUP |  |  | 2014-08-20
| Board of Directors | Ciel Fabros | 8:30 - 11:30 A.M.
| Chairman & Administrator's Office | Ciel Fabros | 8:30 - 11:30 A.M.
| Board Secretariat | Ciel Fabros | 8:30 - 11:30 A.M.
| Intelligence Office | Amy Fernandez | 8:30 - 11:30 A.M.
| Internal Audit Services | Amy Fernandez | 8:30 - 11:30 A.M.
| Planning and Development Office | Amy Fernandez | 8:30 - 11:30 A.M.
| Office of the DA for Corporate Communications | Amy Fernandez | 8:30 - 11:30 A.M.
| Public Relations Office | Amy Fernandez | 8:30 - 11:30 A.M.
| Media Production Office | Amy Fernandez | 8:30 - 11:30 A.M.
INTERNAL SERVICES GROUP |  |  | 2014-08-20
| Office of the SDA for Internal Services | Jo Smallwood | 1:30 - 4:30 P.M.
| Office of the DA for Administration | Jo Smallwood | 1:30 - 4:30 P.M.
| Human Resource & Management Dept. | Jo Smallwood | 1:30 - 4:30 P.M.
| Information Technology Dept. | Nora Sevillejo | 1:30 - 4:30 P.M.
| Office Services Dept. | Nora Sevillejo | 1:30 - 4:30 P.M.
| Procurement & Property Management Dept. | Amy Fernandez | 1:30 - 4:30 P.M.
| Office of the DA for Finance | Ester Tamayo | 1:30 - 4:30 P.M.
| Accounting Dept. | Ester Tamayo | 1:30 - 4:30 P.M.
| Financial Control & Analysis Dept | Ester Tamayo | 1:30 - 4:30 P.M.
| Treasury Dept. | Ester Tamayo | 1:30 - 4:30 P.M.
| Office of the DA for Legal Affairs | Ester Tamayo | 1:30 - 4:30 P.M.
| Legal Dept. | Ester Tamayo | 1:30 - 4:30 P.M.
| Labor Dept. | Ester Tamayo | 1:30 - 4:30 P.M.
Note: 2 pax per dept.

## BUDGET HEARING 2015 (hidden)
BUDGET HEARING SCHEDULE
Tentative Venue: Board Room, Bldg. 229
SBU / DEPARTMENT / OFFICE |  | BUDGET OFFICER | SCHEDULE
BUSINESS AND INVESTMENT GROUP |  |  | 2015-07-13
| Office of the SDA for Business & Investment | Pat Monasterio | 8:30 - 11:30 A.M.
| Land and Asset Management Dept. | Pat Monasterio | 8:30 - 11:30 A.M.
| General Business and Investment | Ciel Fabros | 8:30 - 11:30 A.M.
| Business & Investment - Leisure | Ciel Fabros | 8:30 - 11:30 A.M.
| Business & Investment - Manufacturing & Maritime | Ciel Fabros | 8:30 - 11:30 A.M.
| Business & Investment - ICT | Ciel Fabros | 8:30 - 11:30 A.M.
| Business & Investment - Logistics | Ciel Fabros | 8:30 - 11:30 A.M.
| Office of the DA for Tourism/ Ofc of DA for Buss. Grp | Pat Monasterio | 8:30 - 11:30 A.M.
| Tourism Dept. | Pat Monasterio | 8:30 - 11:30 A.M.
PUBLIC SERVICES GROUP |  |  | 2015-07-13
| Fire Dept. | Boy Peñas | 1:30 - 4:30 P.M.
| Law Enforcement Dept. | Boy Peñas | 1:30 - 4:30 P.M.
| Public Health Department | Boy Peñas | 1:30 - 4:30 P.M.
| Office of the DA for Public Works & Technical Services | Boy Peñas | 1:30 - 4:30 P.M.
| Office of the DA for Public Health and Safety | Boy Peñas | 1:30 - 4:30 P.M.
| Engineering Services | Boy Peñas | 1:30 - 4:30 P.M.
| Construction and Maintenance Dept. | Pat Monasterio | 1:30 - 4:30 P.M.
REGULATORY GROUP |  |  | 2015-07-14
| Office of the SDA for Regulatory Group | Lina Sarmiento | 8:30 - 11:30 A.M.
| Safety Dept. | Lina Sarmiento | 8:30 - 11:30 A.M.
| Ecology Center | Lina Sarmiento | 8:30 - 11:30 A.M.
| Telecommunication Dept. | Lina Sarmiento | 8:30 - 11:30 A.M.
AVIATION AND MARITIME GROUP |  |  | 2015-07-14
| Office of the SDA for Aviation & Maritime Operations | Nora Sevillejo | 1:30 - 4:30 P.M.
| Airport Dept. | Nora Sevillejo | 1:30 - 4:30 P.M.
| Seaport Dept. | Nora Sevillejo | 1:30 - 4:30 P.M.
| Trade Facilitation & Compliance | Nora Sevillejo | 1:30 - 4:30 P.M.
CHAIRMAN & ADMINISTRATOR'S GROUP |  |  | 2015-07-15
| Board of Directors | Ciel Fabros | 8:30 - 11:30 A.M.
| Chairman & Administrator's Office | Ciel Fabros | 8:30 - 11:30 A.M.
| Board Secretariat | Ciel Fabros | 8:30 - 11:30 A.M.
| Intelligence Office | Amy Fernandez | 8:30 - 11:30 A.M.
| Internal Audit Services | Amy Fernandez | 8:30 - 11:30 A.M.
| Planning and Development Office | Amy Fernandez | 8:30 - 11:30 A.M.
| Office of the DA for Corporate Communications | Amy Fernandez | 8:30 - 11:30 A.M.
| Public Relations Office | Amy Fernandez | 8:30 - 11:30 A.M.
| Media Production Office | Amy Fernandez | 8:30 - 11:30 A.M.
INTERNAL SERVICES GROUP |  |  | 2015-07-15
| Office of the SDA for Internal Services | Jo Smallwood | 1:30 - 4:30 P.M.
| Office of the DA for Administration | Jo Smallwood | 1:30 - 4:30 P.M.
| Human Resource & Management Dept. | Jo Smallwood | 1:30 - 4:30 P.M.
| Information Technology Dept. | Jo Smallwood | 1:30 - 4:30 P.M.
| Office Services Dept. | Jo Smallwood | 1:30 - 4:30 P.M.
| Procurement & Property Management Dept. | Jo Smallwood | 1:30 - 4:30 P.M.
| Office of the DA for Finance | Ester Tamayo | 1:30 - 4:30 P.M.
| Accounting Dept. | Ester Tamayo | 1:30 - 4:30 P.M.
| Financial Planning and Budget Dept | Ester Tamayo | 1:30 - 4:30 P.M.
| Treasury Dept. | Ester Tamayo | 1:30 - 4:30 P.M.
| Office of the DA for Legal Affairs | Ester Tamayo | 1:30 - 4:30 P.M.
| Legal Dept. | Ester Tamayo | 1:30 - 4:30 P.M.
| Labor Dept. | Ester Tamayo | 1:30 - 4:30 P.M.
Note: 2 pax per dept.

## PROGRAM forum2015 (hidden)
CY 2015 BUDGET FORUM / WORKSHOP
May 20, 2015 (Wednesday)
SBMA Board Room
PROGRAM
1st SESSION - A.M.
09:00 - 09:05 A.M. | Prayer | Ms. Cielito C. Fabros
09:05 - 09:35 A.M. | Budget Call Presentation | Ms. Editha L. Marzal
09:35 - 09:50 A.M. | PPMP Presentation | PPMD
09:50 - 10:05 A.M. | Performance Based Bonus Presentation | PDO
10:05 - 10:30 A.M. | Question & Answer
2nd SESSION - A.M.
10:30 - 10:35 A.M. | Prayer | Ms. Cielito C. Fabros
10:35 - 11:05 A.M. | Budget Call Presentation | Ms. Editha L. Marzal
11:05 - 11:20 A.M. | PPMP Presentation | PPMD
11:20 - 11:35 A.M. | Performance Based Bonus Presentation | PDO
11:35 - 12:00 NOON | Question & Answer
1st SESSION - P.M.
01:00 - 01:05 P.M. | Prayer | Ms. Cielito C. Fabros
01:05 - 01:35 P.M. | Budget Call Presentation | Ms. Editha L. Marzal
01:35 - 01:50 P.M. | PPMP Presentation | PPMD
01:50 - 02:05 P.M. | Performance Based Bonus Presentation | PDO
02:05 - 02:45 P.M. | Question & Answer
2nd SESSION - A.M.
03:00 - 03:05 P.M. | Prayer | Ms. Cielito C. Fabros
03:05 - 03:35 P.M. | Budget Call Presentation | Ms. Editha L. Marzal
03:35 - 03:50 P.M. | PPMP Presentation | PPMD
03:50 - 4:05 P.M. | Performance Based Bonus Presentation | PDO
04:05 - 04:45 P.M. | Question & Answer
Moderator : Jerome A. Mascardo

## 2015 budget meeting per sbu (hidden)
BUDGET CONSULTATION
Venue: Mini- Board Room, Bldg. 229
February 24,2015
SBU / DEPARTMENT / OFFICE |  | BUDGET OFFICER | SCHEDULE
PUBLIC SERVICES GROUP
| Fire Dept. | Boy Peñas | 9:30 - 10:30 A.M.
| Law Enforcement Dept. | Boy Peñas | 9:30 - 10:30 A.M.
| Public Health Department | Boy Peñas | 9:30 - 10:30 A.M.
| Office of the DA for Public Works & Technical Services | Boy Peñas | 9:30 - 10:30 A.M.
| Engineering Services | Boy Peñas | 9:30 - 10:30 A.M.
| Construction and Maintenance Dept. | Pat Monasterio | 9:30 - 10:30 A.M.
| Information Technology Dept. | Jo Smallwood | 9:30 - 10:30 A.M.
BUSINESS AND INVESTMENT GROUP
| Office of the SDA for Business & Investment | Pat Monasterio | 10:30 - 11:30 A.M.
| Land and Asset Management Dept. | Pat Monasterio | 10:30 - 11:30 A.M.
| General Business and Investment | Ciel Fabros | 10:30 - 11:30 A.M.
| Business & Investment - Leisure | Ciel Fabros | 10:30 - 11:30 A.M.
| Business & Investment - Manufacturing & Maritime | Ciel Fabros | 10:30 - 11:30 A.M.
| Business & Investment - ICT | Ciel Fabros | 10:30 - 11:30 A.M.
| Business & Investment - Logistics | Ciel Fabros | 10:30 - 11:30 A.M.
| Office of the DA for Tourism | Pat Monasterio | 10:30 - 11:30 A.M.
| Tourism Dept. | Pat Monasterio | 10:30 - 11:30 A.M.
REGULATORY GROUP
| Office of the SDA for Regulatory Group | Lina Sarmiento | 1:30 - 2:30 P.M.
| Safety Dept. | Lina Sarmiento | 1:30 - 2:30 P.M.
| Ecology Center | Lina Sarmiento | 1:30 - 2:30 P.M.
| Transportation & Communication Dept. | Lina Sarmiento | 1:30 - 2:30 P.M.
AVIATION AND MARITIME GROUP
| Office of the SDA for Aviation & Maritime Operations | Nora Sevillejo | 1:30 - 2:30 P.M.
| Trade Facilitation & Compliance | Nora Sevillejo | 1:30 - 2:30 P.M.
CHAIRMAN & ADMINISTRATOR'S GROUP
| Board of Directors | Ciel Fabros | 2:30 - 3:30 P.M.
| Chairman & Administrator's Office | Ciel Fabros | 2:30 - 3:30 P.M.
| Board Secretariat | Ciel Fabros | 2:30 - 3:30 P.M.
| Intelligence Office | Amy Fernandez | 2:30 - 3:30 P.M.
| Internal Audit Services | Amy Fernandez | 2:30 - 3:30 P.M.
| Planning and Development Office | Amy Fernandez | 2:30 - 3:30 P.M.
| Office of the DA for Corporate Communications | Amy Fernandez | 2:30 - 3:30 P.M.
| Public Relations Office | Amy Fernandez | 2:30 - 3:30 P.M.
| Media Production Office | Amy Fernandez | 2:30 - 3:30 P.M.
INTERNAL SERVICES GROUP
| Office of the SDA for Internal Services | Jo Smallwood | 3:30 - 4:30 P.M.
| Office of the DA for Administration | Jo Smallwood | 3:30 - 4:30 P.M.
| Human Resource & Management Dept. | Jo Smallwood | 3:30 - 4:30 P.M.
| Office Services Dept. | Jo Smallwood | 3:30 - 4:30 P.M.
| Procurement & Property Management Dept. | Jo Smallwood | 3:30 - 4:30 P.M.
| Office of the DA for Finance | Ester Tamayo | 3:30 - 4:30 P.M.
| Accounting Dept. | Ester Tamayo | 3:30 - 4:30 P.M.
| Financial Control & Analysis Dept | Ester Tamayo | 3:30 - 4:30 P.M.
| Treasury Dept. | Ester Tamayo | 3:30 - 4:30 P.M.
| Office of the DA for Legal Affairs | Ester Tamayo | 3:30 - 4:30 P.M.
| Legal Dept. | Ester Tamayo | 3:30 - 4:30 P.M.
| Labor Dept. | Ester Tamayo | 3:30 - 4:30 P.M.
Note: 2 pax per dept.