## app
|  | Subic Bay Metropolitan Authority Annual Procurement Plan for FY 2021 | [11 empty] | Department of Budget and Management Procurement Monitoring Report as of month/day/2006
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? (Yes/No) | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (brief description of Project) | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [8 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  | Pre-Proc Conf | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Delivery/ Accept
2021-02A | VARIOUS SUPPLIES AND MATERIALS | VARIOUS OFFICES/DEPARTMENTS | NO | Competitive Bidding | 2021-01-04 | 2021-01-25 | 2021-03-29 | 2021-04-08 | Corporate Budget | 90772396.82 | 90772396.82 |  | VARIOUS SUPPLIES AND MATERIALS
2021-02B1 | VARIOUS I.T. EQUIPMENT (SEMI-EXPENDABLE) | MIS | NO | Competitive Bidding | 2021-01-06 | 2021-01-26 | 2021-03-30 | 2021-04-12 | Corporate Budget | 1448266.17 | 1448266.17 |  | VARIOUS I.T. EQUIPMENTS (BOARD SEC, IO, IAS, PRD, MIS, PPMD, OSD, LEGAL, LABOR, ODA FOR FINANCE, TREASURY, OSDA FOR BIG, LADD, ODA FOR INVESTMENT, BID- MFTG. & MARITIME, ICT, TOURISM, FIRE, ENGINEERING, OSDA FOR AVIATION & MARITIME, ODA FOR PORTS OPERATIONS, AIRPORT & TFCD)
2021-02B5 | VARIOUS OTHER EQUIPMENT (SEMI-EXPENDABLE) | MTD | NO | Competitive Bidding | 2021-01-08 | 2021-01-28 | 2021-03-30 | 2021-04-12 | CORPORATE BUDGET | 2524576.34 | 2524576.34 |  | VARIOUS OTHER EQUIPMENTS (CHAD, IO, MIS, HRMD, ODA FOR LEGAL, LEGAL, LABOR, ACCOUNTING, TREASURY, OSDA FOR BIG, LADD, ODA FOR INVESTMENT, BID MFTG. & MARITIME, ICT, TOURISM, FIRE, ODA FOR HEALTH, UTILITIES, MTD, OSDA FOR AVIATION & MARITME OPERATIONS, AIRPORT, SEAPORT, TFCD & ECOLOGY)
2021-03 | FUEL SUPPLY | VARIOUS OFFICES/DEPARTMENTS | NO | Competitive Bidding | 2021-01-11 | 2021-02-01 | 2021-04-05 | 2021-04-15 | CORPORATE BUDGET | 15919940.35 | 15919940.35 |  | FUEL SUPPLY
2021-03 | OILS AND LUBRICANTS | VARIOUS OFFICES/DEPARTMENTS | NO | Competitive Bidding | 2021-01-11 | 2021-02-01 | 2021-04-05 | 2021-04-15 | CORPORATE BUDGET | 1848445.7 | 1848445.7 |  | VARIOUS OILS AND LUBRICANTS
2021-04 | TRAVEL | VARIOUS OFFICES/DEPARTMENTS | NO | NP-53.9 - Small Value Procurement | 2021-01-13 | 2021-02-02 | 2021-04-06 | 2021-04-16 | CORPORATE BUDGET | 3030789 | 3030789 |  | TRAVEL
2021-05 | TRAINING | VARIOUS OFFICES/DEPARTMENTS | NO | NP-53.9 - Small Value Procurement | 2021-01-13 | 2021-02-02 | 2021-04-06 | 2021-04-16 | CORPORATE BUDGET | 2639500 | 2639500 |  | TRAINING
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | NP-53.9 - Small Value Procurement | 2021-01-18 | 2021-02-08 | 2021-04-12 | 2021-04-22 | CORPORATE BUDGET | 200000 | 200000 |  | REPAINTING OF INTERIOR AND EXTERIOR OF BLDG. 494
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | NP-53.9 - Small Value Procurement | 2021-01-18 | 2021-02-08 | 2021-04-12 | 2021-04-22 | CORPORATE BUDGET | 150000 | 150000 |  | REPAINTING AND REPAIR OF BULLETIN BOARDS AT MSD RECEIVING SECTION
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | Competitive Bidding | 2021-01-20 | 2021-02-09 | 2021-04-12 | 2021-04-22 | CORPORATE BUDGET | 7000000 | 7000000 |  | REPAIR & MAINTENANCE OF VARIOUS SBMA BUILDINGS & FACILITIES
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | NP-53.9 - Small Value Procurement | 2021-01-20 | 2021-02-09 | 2021-04-12 | 2021-04-22 | CORPORATE BUDGET | 980000 | 980000 |  | MINOR REPAIR OF STRUCTURALLY FAILED, POTHOLE PATCHING & CRACKSEALING
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | Competitive Bidding | 2021-01-20 | 2021-02-09 | 2021-04-12 | 2021-04-22 | CORPORATE BUDGET | 1200000 | 1200000 |  | MINOR REPAIR OF DRAINAGE SYSTEM
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | Competitive Bidding | 2021-01-22 | 2021-02-11 | 2021-04-13 | 2021-04-23 | CORPORATE BUDGET | 2500000 | 2500000 |  | REPAINTING OF VARIOUS PAVEMENT MARKINGS INCLUDING VARIOUS BRIDGES
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | UTILITIES | NO | Direct Contracting | 2021-01-22 | 2021-02-11 | 2021-04-13 | 2021-04-23 | CORPORATE BUDGET | 6000000 | 6000000 |  | MAINTENANCE OF STREETLIGHTS
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | UTILITIES | NO | Direct Contracting | 2021-01-22 | 2021-02-11 | 2021-04-13 | 2021-04-23 | CORPORATE BUDGET | 3000000 | 3000000 |  | REPAIR AND MAINTENANCE OF WATER LINE AND SEWERAGE LINE
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | Competitive Bidding | 2021-01-25 | 2021-02-15 | 2021-04-19 | 2021-04-29 | CORPORATE BUDGET | 2000000 | 2000000 |  | UPGRADING OF PTB PARKING LIGHTS
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | Competitive Bidding | 2021-01-25 | 2021-02-15 | 2021-04-19 | 2021-04-29 | CORPORATE BUDGET | 3000000 | 3000000 |  | REPAINTING OF AERODROME MARKINGS,
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | NP-53.9 - Small Value Procurement | 2021-01-25 | 2021-02-15 | 2021-04-19 | 2021-04-29 | CORPORATE BUDGET | 500000 | 500000 |  | REHABILITATION OF IN-BUILDING ANALOG AND DATA LINE FOR B8050, 8051,8052
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | Competitive Bidding | 2021-01-28 | 2021-02-18 | 2021-04-21 | 2021-05-03 | CORPORATE BUDGET | 26800000 |  | 26800000 | SVCS & MATLS: UPGRADING OF VARIOUS AERODROME LIGHTING COMPONENTS
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | Competitive Bidding | 2021-01-28 | 2021-02-18 | 2021-04-21 | 2021-05-03 | CORPORATE BUDGET | 3000000 | 3000000 |  | PERIMETER FENCES AND GATES MAINTENANCE
2021-06A | REPAIR & MAINTENANCE OF VARIOUS SBMA BUILDINGS & FACILITIES (LUMPSUM) | MTD | NO | NP-53.9 - Small Value Procurement | 2021-01-18 | 2021-02-07 | 2021-03-08 | 2021-04-07 | Corporate Budget | 7000000 | 7000000 |  | LUMPSUM AMOUNT FOR DAY TO DAY MTD REPAIR WORKS
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | NP-53.9 - Small Value Procurement | 2021-02-01 | 2021-02-22 | 2021-04-06 | 2021-04-16 | CORPORATE BUDGET | 200000 | 200000 |  | PREVENTIVE MAINTENANCE & MISCELLANEOUS REPAIR OF SEAPORT BLDG. (NEW ADMIN B1055,B1018, B291-A, B696),
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | SEAPORT | NO | NP-53.9 - Small Value Procurement | 2021-02-01 | 2021-02-22 | 2021-04-06 | 2021-04-16 | CORPORATE BUDGET | 450000 | 450000 |  | REPAIR & MAINTENANCE OF PIERS & WHARVES
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | NP-53.9 - Small Value Procurement | 2021-02-01 | 2021-02-22 | 2021-04-06 | 2021-04-16 | CORPORATE BUDGET | 775000 | 775000 |  | REPAINTING OF CCTV TOWERS, NSD1, NABASAN, BOTON 1&2,
2021-06A | REPAIR AND MAINTENANCE OF BUILDING FACILITIES | MTD | NO | NP-53.9 - Small Value Procurement | 2021-02-01 | 2021-02-22 | 2021-04-06 | 2021-04-16 | CORPORATE BUDGET | 200000 | 200000 |  | REPAIR AND MAINTENANCE OF B-2005, NAVMAG
2021-06B | REPAIR AND MAINTENANCE OF GOVERNMENT VEHICLES AND WATERCRAFTS | VARIOUS OFFICES/DEPARTMENTS | NO | NP-53.9 - Small Value Procurement | 2021-02-03 | 2021-02-25 | 2021-04-30 | 2021-05-10 | CORPORATE BUDGET | 14590000 | 14590000 |  | REPAIR AND MAINTENANCE OF VARIOUS GOVERNMENT VEHICLES/WATERCRAFTS
2021-06C | REPAIR AND MAINTENANCE OF OTHER EQUIPMENTS | VARIOUS OFFICES/DEPARTMENTS | NO | NP-53.9 - Small Value Procurement | 2021-02-03 | 2021-02-25 | 2021-04-30 | 2021-05-10 | CORPORATE BUDGET | 18328750 | 18328750 |  | REPAIR AND MAINTENANCE OF VARIOUS EQUIPMENTS: AIRCONDITIONING UNITS, ELECTRIC FAN, AIR COOLER, WATER DISPENSER, MIMEOGRAPHING MACHINE, ELETRIC AIRPOT, TYPEWRITER, VARIOUS ICT EQUIPMENT, ANCILLIARY COMPONENTS PERIPHERALS, AND RELATED DEVICES, , OFFICE CHAIRS, REFRIGERATORS, VAULTS, CALCULATORS, MICROWAVE, PORTABLE BASE RADIO, LEAF BLOWER, KARO, LABORATORY AND MEDICAL EQUIPMENTS, PREVENTIVE MAINTENANCE OF DETECTORS AND X-RAY MACHINES, SURVEY INSTRUMENTS, GENERATOR SETS, POLE PRUNER, ELECTRIC TOOLS, BICYCLE, TOWER LIGHTS, CHAINSAWS, BRUSH CUTTER/WEEDEATERS, ELECTRONIC SYSTEMS AND DEVICES, PABX EQUIPMENT, UNINTERRUPTIBLE POWER SUPPLY, CHILLERS, ELEVATORS, ESCALATORS, CONVEYORS, EVAPORATORS, AGL, LOAD SIDE CABLE, LED LIGHTS OF RUNWAY AND TAXIWAYS LIGHTS, SHOP AND DIVING EQUIPMENT, AUXILLIARY SYSTEM, NAVIGATIONAL AIDS, VTMS,
2021-18 | ALL OTHER SERVICES | LEGAL/LABOR & AIRPORT | NO | NP-53.9 - Small Value Procurement | 2021-02-05 | 2021-03-01 | 2021-05-03 | 2021-05-13 | CORPORATE BUDGET | 2441000 | 2441000 |  | ALL OTHER SERVICES Docket Fees/Filing Fees/Transcript of Stenographic Notes, Special Events - Labor Matching Congress/Bridging the Cultural Gaps in the Workplace/Livelihood Training Programs, Digitizing various SBIA phone, Safety Audit Inspection
2021-18 | ALL OTHER SERVICES | CHAD/PDO & ODA FOR BUSINESS & INVESTMENT | NO | NP-53.9 - Small Value Procurement | 2021-02-05 | 2021-03-01 | 2021-05-03 | 2021-05-13 | CORPORATE BUDGET | 2602500 | 2602500 |  | ALL OTHER SERVICES Misc Expenses Management & Various Committee Meetings
2021-18 | ALL OTHER SERVICES | CHAD/PRD/MPD/LADD/AIRPORT/OSDA FOR REGULATORY & ECOLOGY | NO | Competitive Bidding | 2021-02-05 | 2021-03-01 | 2021-05-03 | 2021-05-13 | CORPORATE BUDGET | 3246325 | 3246325 |  | ALL OTHER SERVICES Meals/Food Provision
2021-18 | ALL OTHER SERVICES | VARIOUS OFFICES/DEPARTMENTS | NO | NP-53.9 - Small Value Procurement | 2021-02-08 | 2021-03-04 | 2021-05-07 | 2021-05-17 | CORPORATE BUDGET | 16926793 | 16926793 |  | ALL OTHER SERVICES MISCELLANEOUS (ISO Cert, /membership dues, tokens) , docket&filing fees), flowers, purified drinking water, media meter, picture frame), honoraria, forums, NLRC,CIBI
2021-08 | Outsourcing of Grass Cutting/ Ground Maintenance/ Street Sweeping & Maintenance and Landscape areas | MTD | YES | Competitive Bidding | 2020-10-01 | 2020-10-22 | 2020-12-11 | 2020-12-21 | CORPORATE BUDGET | 60030455.33 | 60030455.33 |  | ALL OTHER SERVICES MISCELLANEOUS Outsourcing of Grass Cutting/ Ground Maintenance/ Street Sweeping & Maintenance and Landscape areas
2021-08 | Outsourcing of Services | MTD | YES | Competitive Bidding | 2020-10-01 | 2020-10-22 | 2020-12-11 | 2020-12-21 | CORPORATE BUDGET | 21582723.84 | 21582723.84 |  | ALL OTHER SERVICES MISCELLANEOUS Outsourcing of Janitorial Services
2021-08 | Outsourcing of Services | LED | YES | Competitive Bidding | 2020-10-02 | 2020-10-23 | 2020-12-14 | 2020-12-23 | CORPORATE BUDGET | 24220206.78 | 24220206.78 |  | ALL OTHER SERVICES MISCELLANEOUS Outsourcing of Security-Buildings
2021-08 | Outsourcing of Services | LED | YES | Competitive Bidding | 2020-10-02 | 2020-10-23 | 2020-12-14 | 2020-12-23 | CORPORATE BUDGET | 41240600.94 | 41240600.94 |  | ALL OTHER SERVICES MISCELLANEOUS Outsourcing of Security-Housings
2021-08 | Outsourcing of Services | LED | YES | Competitive Bidding | 2020-10-02 | 2020-10-23 | 2020-12-14 | 2020-12-23 | CORPORATE BUDGET | 37334934.45 | 37334934.45 |  | ALL OTHER SERVICES MISCELLANEOUS Outsourcing of Security-Traffic Management
2021-08 | Outsourcing of Services | LED | YES | Competitive Bidding | 2020-10-02 | 2020-10-23 | 2020-12-14 | 2020-12-23 | CORPORATE BUDGET | 4968505.08 | 4968505.08 |  | ALL OTHER SERVICES MISCELLANEOUS Outsourcing of Security-Innergate
2021-08 | Outsourcing of Services | LED | YES | Competitive Bidding | 2020-10-02 | 2020-10-23 | 2020-12-14 | 2020-12-23 | Corporate Budget | 9937010.16 | 9937010.16 |  | ALL OTHER SERVICES MISCELLANEOUS Outsourcing of Security-Aviation
2021-08 | Outsourcing of Services | SEAPORT | YES | Competitive Bidding | 2020-10-01 | 2020-10-22 | 2020-12-11 | 2020-12-21 | CORPORATE BUDGET | 37055065.45 | 37055065.45 |  | ALL OTHER SERVICES MISCELLANEOUS Outsourcing of Cargo Checkers
2021-09 | RENTS | TELECOMS | NO | Competitive Bidding | 2021-02-08 | 2021-03-04 | 2021-05-07 | 2021-05-17 | CORPORATE BUDGET | 5344714.21 | 5344714.21 |  | RENTS Handheld Radio
2021-09 | RENTS | MTD | NO | NP-53.9 - Small Value Procurement | 2021-02-08 | 2021-03-04 | 2021-05-07 | 2021-05-17 | CORPORATE BUDGET | 2000000 | 2000000 |  | RENTS Heavy Equipment
2021-09 | RENTS | TOURISM/MTD | NO | Competitive Bidding | 2021-02-08 | 2021-03-04 | 2021-05-07 | 2021-05-17 | CORPORATE BUDGET | 1200000 | 1200000 |  | RENTS Portalet
2021-20 | INFORMATON TECHNOLOGY | VARIOUS OFFICES/DEPARTMENTS/MIS | NO | Competitive Bidding | 2021-02-22 | 2021-03-15 | 2021-05-18 | 2021-05-28 | CORPORATE BUDGET | 91971962 |  | 91971962 | Network Transport Upgrade / Network, Infrastructure, Fiber Connection, Camera, Digital, HIGH END, System, Enterprise Resource Planning System / Customer Relationship Management System, GIS Upgrade, Computer, Desktop, With Operating System, Software, Office Productivity Tools, Uninterruptible Power Supply (UPS), Computer, Laptop, With Operating System, Printer,Ink-tank system, Colored, Multi-function, Printer,Ink-tank system, Colored, Multi-function, A3, Interactive Screen / Smart TV, Scanner, Computer, Laptop, With Operating System, Camera, Digital, HIGH END, Printer,Laser, Monochrome, Printer,Barcode, Printer, Laser, Colored, Heavy Duty, Multi-function, Camera, Action, Scanner, Server, Computer (Specialized, CIQ), Scanner, Large Format, Projector, Multimedia, Dive Computer, Projector, Multimedia, TABLET, 1O", Printer, Technical Print and Cut),
2021-25 | MOTOR VEHICLES & HEAVY EQUIPMENTS | VARIOUS OFFICES/DEPARTMENTS/MTD | NO | Competitive Bidding | 2021-02-22 | 2021-03-15 | 2021-05-18 | 2021-05-28 | CORPORATE BUDGET | 200189000 |  | 200189000 | PASSENGER VAN, MULTI-PURPOSE VEHICLE, HVY. EQPT. STAKE TRUCK, LIGHT VEHICLE, MOTORCYCLE, 400CC OR ABOVE (MOTORCYCLE, H-WAY PATROL) w/ complete accessories, LIGHT VEHICLE, MOTORCYCLE, 800CC to 1000 OR ABOVE (MOTORCYCLE, H-WAY PATROL) w/ complete accessories, PATROL CAR, AUV, AMBULANCE, TYPE II, AMBULANCE, TYPE III, PICK-UP, HEAVY EQPT, Dropside Cargo Truck (Boom Truck w/ a capacity of 2.9 tons Kato crane with 3 section boom or similar, Heavy Eqpt, Aerial Flatform Truck w/ Bucket, Heavy Eqpt, Carrying Truck, HEAVY EQPT, LOADER BACKHOE, HVY. EQPT. WATER TANK TRUCK (for replacement), HVY. EQPT. WRECKER/TOW TRUCK, HVY. EQPT. BUCKET BOOM TRUCK,
2021-23 | OTHER EQUIPMENTS | TELECOMS | NO | Competitive Bidding | 2021-02-24 | 2021-03-17 | 2021-05-20 | 2021-05-30 | GoP | 12500000 |  | 12500000 | TRAFFIC CONTROL SYSTEM (2 new)
2021-23 | OTHER EQUIPMENTS | TELECOMS/SEAPORT | NO | Competitive Bidding | 2021-02-24 | 2021-03-17 | 2021-05-20 | 2021-05-30 | CORPORATE BUDGET | 68560000 |  | 68560000 | Modernization of ISPS CCTV Surveillance System, Services and Materials for the procurement of 911 Universal Public Safety/Security Answering Point System, CELLULAR SIGNAL REPEATER, TRIBAND
2021-23 | OTHER EQUIPMENTS | TREASURY/FIRELED/AIRPORT/SEAPORT/MTD/ENGINEERING/TELECOMS/TOURISM | NO | NP-53.9 - Small Value Procurement | 2021-02-24 | 2021-03-17 | 2021-05-20 | 2021-05-30 | CORPORATE BUDGET | 15490700 |  | 15490700 | MONEY COUNTER AND COUNTERFEIT DETECTOR, COMPRESSOR, HIGH PRESSURE, electrical with 5,075 PSI, PORTABLE FIRE PUMP, NOZZLE, TURBOJET W/ PISTOL GRIP 1 1/2", NOZZLE, TURBOJET W/ PISTOL GRIP 2 1/2", OUTBOARD MOTOR , PATROL BOAT , 115HP, 4 STROKE,gasoline engine, electric start, PROCUREMENT OF AWOS CRITICAL SPAREPARTS, FIRE PROTECTION FOR VARIOUS EQUIPMENT, SERVER AND ELECTRICAL ROOMS, SUPPLY, DELIVERY AND INSTALLATION OF CHILLER, CHIPPING GUN, ROTARY HAMMER WITH SHOCKS, WINGTRAONE VTOL DRONE FOR MAPPING AND SURVEYING, Mobile Tower Lights, Services and Materials for the Installation of Grid-Tied Solar Power System at Bldg. 225, Services and Materials for the Installation of Grid-Tied Solar Power System at Bldg. 662, Upgrade of Regulatory Bldg Grid-Tied Solar Power System, Installation of Centralized Appliance control system for Air Conditioning Units at Regulatory Bldg, Supply, Delivery & Installation of 100KVA & 75 KVA Mobile Power Generators including Manual Transfer Switches and Electrical Wiring and Accessories, PORTABLE VOLLEYBALL POST SYSTEM WITH REFEREE STAND, ADJUSTABLE VOLLEYBALL REFEREE CHAIR, MOVABLE BADMINTON SYSTEM WITH UMPIRE SEAT
2021-23 | OTHER EQUIPMENTS | AIRPORT | NO | Competitive Bidding | 2021-02-26 | 2021-03-19 | 2021-05-24 | 2021-06-03 | GoP | 35000000 |  | 35000000 | VARIOUS SECURITY SCREENING EQUIPMENT
2021-01A | POWER | UTILITIES | NO | Direct Contracting | N/A | N/A | N/A | N/A | CORPORATE BUDGET | 84165584.04 | 84165584.04 |  | WITH EXISTING FRANCHISE CONTRACT TO SUBIC ENERZONE CORPORATION
2021-01B | WATER | UTILITIES | NO | Direct Contracting | N/A | N/A | N/A | N/A | CORPORATE BUDGET | 5864343.36 | 5864343.36 |  | WITH EXISTING FRANCHISE CONTRACT TO SUBIC WATER AND SEWERAGE COMPANY, INC.
2021-05 | LANDLINE/LEASED LINES, VOX PABX, HOTLINE, PABX, MOBILE BROADCAST, INTERNET, NTC DATA TRANSPORT, WEB-EMAIL SOFTWARE CAD (SUBSCRIPTION) (ISP), AIRFREIGHT/COURIER AND POSTAL | TELECOMS/MIS AND OSD | NO | Direct Contracting | N/A | N/A | N/A | N/A | CORPORATE BUDGET | 18389342.05 | 18389342.05 |  | PLDT- LANDLINE/LEASED LINES, VOX PABX, PLDT HOTLINE, PABX-PLDT/SMART, MOBILE-GLOBE/SMS BROADCAST, INTERNET - DSL, NTC DATA TRANSPORT, WEB-EMAIL SOFTWARE CAD (SUBSCRIPTION) PLDT/DSL (ISP), AIRFREIGHT/COURIER AND PPC POSTAL
2021-02B | VARIOUS OFFICE EQUIPMENT (SEMI-EXPENDABLE) | MTD | NO | Shopping | 2021-01-05 | N/A | 2021-02-05 | 2021-02-15 | CORPORATE BUDGET | 147110.51 | 147110.51 |  | VARIOUS OFFICE EQUIPMENTS (CHAD, IO, MIS, PPMD, ODA LEGAL, LEGAL, TREASURY, LADD, TOURISM & ENGINEERING)
2021-02B2 | VARIOUS ELECTRONICS & COMMUNICATIONS EQUIPMENT (SEMI-EXPENDABLE) | TELECOMS | NO | Shopping | 2021-01-19 | N/A | 2021-02-19 | 2/29/2021 | CORPORATE BUDGET | 418184.6 | 418184.6 |  | VARIOUS ELECTRONICS & COMMUNICATIONS EQUIPMENTS (PRD, OSD, ODA FOR LEGAL, LEGAL, LABOR, ACCOUNTING, TOURISM, FIRE, LED, TELECOMS, AIRPORT & ECOLOGY)
2021-02B3 | VARIOUS MEDICAL EQUIPMENT (SEMI-EXPENDABLE) | PHSD | NO | Shopping | 2021-01-27 | N/A | 2021-03-01 | 2021-03-10 | CORPORATE BUDGET | 24000 | 24000 |  | MEDICAL EQUIPMENTS (AIRPORT)
2021-02B4 | VARIOUS OTHER EQUIPMENT (SEMI-EXPENDABLE) | TELECOMS | NO | Shopping | 2021-01-28 | N/A | 2021-03-02 | 2021-03-11 | CORPORATE BUDGET | 7400 | 7400 |  | OTHER EQUIPMENTS (BOARD SEC)
2021-18 | ALL OTHER SERVICES | PRD/PHSD/TELECOMS/SEAPORT | NO | NP-53.5 Agency-to-Agency | N/A | N/A | 2021-01-04 | 2021-01-14 | CORPORATE BUDGET | 212500 | 212500 |  | ALL OTHER SERVICES Participation Fee/Membership dues
2021-18 | ALL OTHER SERVICES | MTD | NO | NP-53.5 Agency-to-Agency | N/A | N/A | 2021-01-04 | 2021-01-14 | CORPORATE BUDGET | 581400 | 581400 |  | ALL OTHER SERVICES LTO Registration, Smoke Emmission and Storage Fee
2021-18 | COMMON-USE SUPPLIES AND EQUIPMENTS (CSE) | PPMD | NO | NP-53.5 Agency-to-Agency | N/A | N/A | N/A | N/A | Corporate Budget | 8966401.47 | 8966401.47 |  | AVAILABLE AT PS-DBM (SEE APP-CSE 2021 FOR REFERENCE))
2021-18 | CSE FOR STOCKING | PPMD | NO | Competitive Bidding | 2021-01-04 | 2021-01-25 | 2021-03-29 | 2021-04-08 | Corporate Budget | 19737260.23 | 19737260.23 |  | STOCKING ITEMS NOT AVAILABLE AT PS-DBM (SEE APP-CSE 2021 FOR REFERENCE)
2021-18 | ALL OTHER SERVICES | VARIOUS OFFICES/DEPARTMENTS | NO | NP-53.5 Agency-to-Agency | N/A | N/A | 2021-01-04 | 2021-01-14 | CORPORATE BUDGET | 19285240.97 | 19285240.97 |  | ALL OTHER SERVICES Fidelity Bonds & Insurance Premiums
2021-07 | ADVERTISEMENT AND PROMOTIONS | VARIOUS OFFICES/DEPARTMENTS | NO | NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | N/A | N/A | 2021-01-07 | 2021-01-17 | CORPORATE BUDGET | 31143714 | 31143714 |  | VARIOUS TOURISM ADVERTISEMENT AND PROMOTIONS, PRODUCTION AND PRINT (10TH POINT AGENDA), INVITATION TO BID VARIOUS SBMA SCRAP/UNSERVICEABLE ASSETS, NEWSPAPER PUBLICATION, TARPAULIN PRINTING, SBMA SHARE FOR THE PHIL. INVESTMENTMENTS PROMOTION PLAN (PIPP), HOSTING OF PIPP MEMBERS DURING PIPP MEETING IN SBFZ, SBMA'S AUDIO-VISUAL PRESENTATION, BUSINESS AND INVESTMENT GROUP CORPORATE GIVE-AWAYS/TOKENS, INVESTMENT BROCHURE, ADVERTISEMENT FOR PROPERTY APPRAISAL OF SELECTED HOUSING UNITSBASED ON THE CURRENT MARKET VALUE, ADVERTISEMENT FOR HIRING OF SERVICE OF A PRIVATE SURVEYOR, ADVERTISING AND PUBLICATION NEWSPAPER/NATIONAL CIRCULATION, INFLIGHT, LIFESTYLE AND TRAVEL MAGAZINES SUBSCRIPTION, TV INFO COMMERCIALS, LOCAL AND INTERNATIONAL, LIFESTYLE AND TRAVEL, NLEX/SLEX/METRO MANILA/AIRPORT ADVERTISEMENTS, PROMOTIONAL PARTICIPATION TO VARIOUS MICE AND TRAVEL FAIRS (ABROAD & LOCAL), COLLATERALS, PRINTING SERVICES, EZ MAP BROCHURES, SOUVENIRS, FANS, TOURISM MEMBERSHIP, CRUISE SHIP ARRIVALS, SPECIAL EVENTS, CUSTOM MADE MASCOT, FIRE PREVENTION MONTH/FIRE OLYMPICS, ADVERTISING/PUBLICATION SUBIC FREEPORT AS GATEWAY /NEW POLICIES/POLICIES ON FINES, PENALTIES & FEES, ANTI-LITTERING POLICY, PROHIBITING USE OF PLASTIC BAG, REVISED ALLOWABLE TREE CUTTING, ANTI-SMOKE BELCHING
2021-18 | ALL OTHER SERVICES | VARIOUS OFFICES/DEPARTMENTS | NO | NP-53.9 - Small Value Procurement | 2021-01-04 | N/A | 2021-02-04 | 2021-02-14 | CORPORATE BUDGET | 416519 | 416519 |  | ALL OTHER SERVICES newspaper/ other subscription
300-01-01 | REPAIR OF BLDG. 662 TOILETS | MTD/PDO | NO | Competitive Bidding | 2021-02-15 | 2021-03-07 | 2021-04-05 | 2021-04-15 | Corporate Budget | 2500000 | 2500000
300-08-02 | RENOVATION OF BLDG. 657 | ENGG/LED | NO | Competitive Bidding | 2021-01-04 | 2021-01-24 | 2021-02-22 | 2021-03-14 | Corporate Budget | 20200000 | 20200000
400-09-01 | UPGRADING OF VESSEL TRAFFIC MONITORING SYSTEM (VTMS) | SEAPORT | YES | Competitive Bidding | 2021-02-02 | 2021-02-22 | 2021-03-23 | 2021-04-12 | GoP | 270000000 |  | 270000000 | (Proposed NG Funded Project, Awaiting approval of GAA for fund source and inclusion in Early Procurement Activity)
400-09-02 | IMPROVEMENT OF SBIA BUILDING FACILITIES (B-8015, B-8050, ATC TOWER CAB) | ENGG/AIRPORT | YES | Competitive Bidding | 2021-02-02 | 2021-02-22 | 2021-03-23 | 2021-04-12 | GoP | 61000000 |  | 61000000 | (Proposed NG Funded Project, Awaiting approval of GAA for fund source and inclusion in Early Procurement Activity) | [29 empty] | TOTAL | 1407800000
400-09-03 | REHABILITATION OF SEAPORT FACILITIES | ENGG/SEAPORT | NO | Competitive Bidding | 2021-01-04 | 2021-01-25 | 2021-03-29 | 2021-04-08 | Corporate Budget | 58800000 |  | 58800000 | BOTON WHARF APRON, BOTON ROAD NETWORK, CARGO CONTROL BRANCH OFFICE(TIPO), PUBLIC RESTROOMS AT NSD COMPOUND, NSD PERIMETER FENCE, REPAIR OF POTHOLES AT MARINE TERMINAL, TERMINAL OPERATIONS DIVISION OFFICE BUILDING (NSD COMPOUND), RE-INSTALLATION OF CONCRETE BLOCKS AT LEYTE WHARF, REPAIR OF BLDG. 1010 PHASE 2, ILLUMINATION OF SATTLER PIER, REHABILITATION OF SATTLER PIER | [29 empty] | MOOE | 22700000
400-07-04 | CONSTRUCTION OF NEW UPPER BINICTICAN BRIDGE | ENGG | NO | Competitive Bidding | 2021-05-01 | 2021-05-21 | 2021-06-19 | 2021-07-09 | Corporate Budget | 15000000 |  | 15000000 | [30 empty] | CAPEX | 1385100000
400-09-05 | REPAIR AND REHABILITATION OF AIRCRAFT PAVEMENT AT CHARLIE TAXIWAY, SOUTHWEST AND BOTON APRON | AIRPORT | NO | Competitive Bidding | 2021-06-14 | 2021-07-04 | 2021-08-02 | 2021-09-01 | GoP | 114300000 |  | 114300000 | (Proposed NG Funded Project, Awaiting approval of GAA for fund source and inclusion in Early Procurement Activity)
400-07-06 | ROAD REHABILITATION PROJECT 2021 | ENGG | YES | Competitive Bidding | 2020-09-15 | 2020-10-05 | 2020-11-03 | 2020-12-03 | GoP | 225000000 |  | 225000000
400-07-07 | IMPLEMENTATION OF DRAINAGE MASTERPLAN | ENGG | YES | Competitive Bidding | 2020-10-06 | 2020-10-26 | 2020-11-24 | 2020-12-24 | GoP | 590000000 |  | 590000000
400-07-08 | PERIMETER FENCE PHASE 2 | ENGG | YES | Competitive Bidding | 2020-10-06 | 2020-10-26 | 2020-11-24 | 2020-12-24 | GoP | 51000000 |  | 51000000
2021-01 | EXECUTIVE ASSISTANTS | BOARD SECRETARIAT | NO | NP-53.7 Highly Technical Consultants | N/A | N/A |  |  | Corporate Budget | 1123920 | 1123920 |  | Hiring of 3 Executive Assistants under the Board Secretariat (Ex. Asst. 1-pax (Php35,105.00/mo)/ Ex. Asst. 2-pax (Php58,554.20mo)
2021-01 | OFFICE CONSULTANTS | MEDIA PRODUCTION DEPARTMENT | YES | NP-53.7 Highly Technical Consultants | N/A | N/A |  |  | Corporate Budget | 3443100 | 3443100 |  | Hiring of 4pax highly technical consultants under MPD (1-pax SG-16 (P35,106/mo)/ 1-pax SG-22 (P66,867/mo),/1-pax SG-23 (P75,359/m0)/ 1-pax SG-26(109,593/mo) | [29 empty] | TOTAL | 160702135.98
2021-02 | APPRAISAL OF VARIOUS UNSERVICEABLE PROPERTIES FOR DISPOSAL | PPMD | NO | NP-53.7 Highly Technical Consultants |  |  |  |  | Corporate Budget | 150000 | 150000 |  | Procurement of services for the appraisal of various U/S properties for disposal. | [29 empty] | MOOE | 88538720
2021-04 | OFFICE CONSULTANTS | ACCOUNTING DEPARTMENT | YES | NP-53.7 Highly Technical Consultants | N/A | N/A |  |  | Corporate Budget | 3791450 | 3791450 |  | Hiring of office consultants (SG-19) under Accounting Department | [29 empty] | CAPEX | 72163415.98
2021-05 | OFFICE CONSULTANTS | LADD | YES | NP-53.7 Highly Technical Consultants | N/A | N/A |  |  | Corporate Budget | 1722760 | 1722760 |  | Hiring of individual office consultants for the inventory of all SBMA fixed assets
2021-08 | OFFICE CONSULTANT | LED | YES | NP-53.7 Highly Technical Consultants | N/A | N/A |  |  | Corporate Budget | 321050 | 321050 |  | Hiring of office consultant under LED (SG13) | [29 empty] | PROJDECT | 68175000 | 96675000
2021-08 | MEDICAL PROFESSIONALS | PHSD | YES | NP-53.7 Highly Technical Consultants | N/A | N/A |  |  | Corporate Budget | 4047280 | 4047280 |  | Hiring of various medical professionals under PHSD (Radiologist-3pax SG18 (P42,159/mo/)/ OB-Gyne-1pax SG18 (P42,159/MO)/ Internal Medicine-1pax SG18 (P42,159/mo)/ Psychologist SG18 (P42,159/mo)/ Community Health Ofr- 2pax SG18 (P42,159/mo) | [29 empty] | OFFICE | 20363720
2021-07 | OFFICE CONSULTANTS | ENGINEERING DEPARTMENT | YES | NP-53.7 Highly Technical Consultants | N/A | N/A |  |  | Corporate Budget | 1925380 | 1925380 |  | Hiring of various Office Consultants under Engineering Dept (CE- SG22) (P66,876/MO)/ CE-G19 (P93,581/mo) | [30 empty] | 88538720
2021-07 | OFFICE CONSULTANTS | MTD | YES | NP-53.7 Highly Technical Consultants | N/A | N/A |  |  | Corporate Budget | 802400 | 802400 |  | Hiring of office consultant under MTD 1pax SG13 (P66,867/mo)
2021-09 | OFFICE CONSULTANTS | AIRPORT DEPARTMENT | YES | NP-53.7 Highly Technical Consultants | N/A | N/A |  |  | Corporate Budget | 1823290 | 1823290 |  | Hiring of highly technical consultant under Airport dept. 1pax-SG24 (P66,867/mo)/ 1pax-SG25 (P85,074/mo)
2021-10 | OFFICE CONSULTANT | OSDA FOR REGULATORY | YES | NP-53.7 Highly Technical Consultants | N/A | N/A |  |  | Corporate Budget | 702650 | 702650 |  | Hiring of office consultant for GAD 1pax - SG16 (P58,554/mo)
2021-10 | CONSULTANCY FOR THE AUTOMATION OF THE APPLICATION AND PERMIT SYSTEM | ECOLOGY DEPARTMENT | NO | Competitive Bidding |  |  |  |  | Corporate Budget | 510440 | 510440 |  | Hiring of consultancy services for automation of the application and permit system
CONS-300-05-01 | CONSULTANCY SERVICES FOR THE APPRAISAL OF SBMA FIXED ASSETS | LADD | NO | Competitive Bidding | 2021-02-15 | 2021-03-07 | 2021-04-05 | 2021-04-15 | Corporate Budget | 10175000 | 10175000 |  | Procurement of consultancy services for appraisal of SBMA fixed assets
CONS-300-05-02 | SERVICES OF PRIVATE SURVEYOR-TO PREPARE THE PROPERTY ADDRESSING OF THE SBFZ PER DISTRICT FOR PROPER AREA IDENTIFICATION | LADD | NO | Competitive Bidding | 2021-05-01 | 2021-05-21 | 2021-06-19 | 2021-07-09 | Corporate Budget | 2000000 | 2000000 |  | Procurement of services for the preparation of property addressing per district for proper area identification
CONS-300-09-03 | CONSULTANCY SERVICES FOR THE FORMULATION AND IMPLEMENTATION OF A DIVESTMENT STRUCTURE FOR SUBIC BAY INTERNATIONAL AIRPORT | AIRPORT | NO | Competitive Bidding | 2021-05-01 | 2021-05-21 | 2021-06-19 | 2021-07-09 | Corporate Budget | 6000000 | 6000000 |  | Procurement of services for the formulation and implementation of divestment structure at SBIA.
CONS-300-10-06 | CONSULTANCY SERVICES FOR THE UPDATING ON SUBIC BAY PROTECTED AREA MANAGEMENT PLAN (SBPAMP) BASELINE STUDIES | ECOLOGY | NO | Competitive Bidding | 2021-02-15 | 2021-03-07 | 2021-04-05 | 2021-04-15 | Corporate Budget | 50000000 | 50000000 |  | Procurement of services fot the updating on sbpamp baseline studies. | [30 empty] | 72163415.98
CONS-400-01-01 | CONSULTANCY SERVICE FOR THE PREPARATION OF DETAILED ENGINEERING DESIGN & CONSTRUCTION SUPERVISION FOR VARIOUS PLANNING & DEVELOPMENT OFFICE PROJECTS | ENGG/PDO | NO | Competitive Bidding | 2021-06-14 | 2021-07-04 | 2021-08-02 | 2021-09-01 | Corporate Budget | 30271384.32 |  | 30271384.32
CONS-400-07-02 | CONSULTING SERVICES FOR THE PREPARATION OF DETAILED ENGINEERING DESIGN AND CONSTRUCTION SUPERVISION FOR THE WIDENING OF RIZAL HIGHWAY FROM 14TH STREET TO MANILA AVENUE INCLUDING EXPANSION OF KALALAKE BRIDGE | ENGG | NO | Competitive Bidding | 2021-04-15 | 2021-05-05 | 2021-06-03 | 2021-07-03 | CORPORATE BUDGET | 24892031.66 |  | 24892031.66
CONS-400-07-03 | CONSULTANCY SERVICES FOR THE REVIEW AND UPDATING OF DETAILED ENGINEERING DESIGN AND CONSTRUCTION SUPERVISION OF THE PROPOSED PEDESTRIAN FOOTBRIDGE | ENGG | NO | Competitive Bidding | 2021-04-15 | 2021-05-05 | 2021-06-03 | 2021-07-03 | CORPORATE BUDGET | 8000000 |  | 8000000
CONS-400-07-04 | CONSULTANCY SERVICES FOR THE PREPARATION OF DETAILED ENGINEERING DESIGN AND CONSTRUCTION SUPERVISION FOR THE CLOSURE OF LANDFILL | ENGG/MTD | NO | Competitive Bidding | 2021-02-26 | 2021-03-18 | 2021-04-16 | 2021-05-16 | CORPORATE BUDGET | 8000000 |  | 8000000
CONS-400-07-05 | CONSULTANCY SERVICE FOR THE PREPARATION OF DETAILED ENGINEERING DESIGN AND CONSTRUCTION SUPERVISION FOR THE CONSTRUCTION OF NEW UPPER BINICTICAN BRIDGE | ENGG | NO | Competitive Bidding | 2021-01-04 | 2021-01-25 | 2021-03-29 | 2021-04-08 | Corporate Budget | 1000000 |  | 1000000
0
0
0
2021-09 | RENTS | VARIOUS OFFICES/DEPARTMENTS | NO | Competitive Bidding | 2020-08-20 | ON GOING | ON GOING | ON GOING | CORPORATE BUDGET | 7298257.2 | 7298257.2 |  | RENTS Photocopying Services (On-Going Process)

## how_to_fill_out-definitions
| GUIDE TO PREPARE APP | APP COLUMN HEADER/S
STEP 1 | In the Code column, kindly indicate the PAP Code. Please refer to the code indicated in the technical budget posted in the DBM website. For GOCCs and LGUs, indicate the procuring entity's internal numbering system. | Code (PAP)
STEP 2 | For the Procurement Project column, please align descriptions of program/projects with budget documents and ensure clarity and accuracy in describing each procurement program/project. | Procurement Project
STEP 3 | For PMO/End-User, please indicate the PMO/End-User unit who will implement/utilize the procurement program/project. Multiple end-user units are allowed only if the procurement activity was consolidated by the BAC to procure requirements of the end-user units. | PMO/End-User
STEP 4 | For Mode of Procurement and Schedule for Each Procurement Activity, all modes of procurement are available as a dropdown list and requirements for a specific schedule for Ads/Post of IB/REI, Sub/Open of Bids, Notice of Award, and/or Contract Signing are automatically identified thru the MS Excel formula. Note that for Foreign-funded procurement, please use Others - Foreign-funded procurement as the Mode of Procurement. Kindly indicate a specific period (dates, month, quarter) when each Procurement Activity will be done. Please refer to our website: http://www.gppb.gov.ph/timelines/timelines.htm for the specific periods for each activity. Note: For SVP, IB/REI is similar to RFQ. Ads/Post of IB/REI for Shopping 52.1(b) and NP-SVP (53.9) needs to be posted in PhilGEPS for ABCs above 50k. Notice of Award posting in PhilGEPS is mandatory for all Alternative Modes only for ABCs above 50k. | Mode of Procurement | Schedule for Each Procurement Activity
|  |  | Ads/Post of IB/REI | Sub/Open of Bids | Notice of Award | Contract Signing
STEP 5 | For Source of Funds, a dropdown list is available. If the Source of Funds the PE will use is not included, please indicate "Others" and specify under the Remarks column. | Source of Funds
STEP 6 | For Estimated Budget (PhP), kindly fill out either MOOE or CO columns only. Total ABC column is not editable, but will automatically compute for the total MOOE and CO components of the project. This breakdown is needed for tracking purposes. Finally, please ensure that amounts indicated are aligned with budget documents. | Estimated Budget (PhP)
STEP 7 | Before submission to the GPPB, ensure that the Head of the Procuring Entity (HoPE) approves/signs the APP.
GENERAL INFORMATION
#1 | All Cells with Fill Color Orange needs to be filled out by the Agency. This is a visual reminder of blank or improperly filled out cells.
#2 | To ensure that automated indicator which procurement activity needs to be filled out with specific periods, PE must copy entire Excel row with the mode of procurement for the specific procurement program/project and paste on the last sample row "Negotiated Procurement-53.13" in the template.
#3 | If PE wishes to edit formatting and design of borders, fonts, among others of the APP template, it is suggested to utilize the automated formulas in the template before copying contents and reformatting.
#4 | Per Section of 3.1.1 of DBM Circular No. 2015-7, the Approved Budget for the Contract (ABC) shall be “[t]he amount reflected in the MYOA”. Hence, the ABC in the Annual Procurement Plan (APP) shall be the full amount stated in the MYOA with remarks added on how much will be actually disbursed for that particular fiscal year. Moreover, the Procurement Monitoring Report (PMR) should also reflect full amount in the MYOA if the entire contract was awarded within the fiscal year. Thus, for succeeding years, actual disbursements from the MYOA need not be reflected in the APPs and PMRs, unless current contract with MYOA is terminated and a new procurement activity is undertaken.
DEFINITIONS
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (advertising/posting; submission and receipt/Opening of bids; award of contract; contract signing).
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund
7. Estimated Budget - Agency approved estimate of project/program costs
8. Remarks - brief description of program or project

## data_validation (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
Emergency Procurement under the Bayanihan Act
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets
Others - Foreign-funded procurement